Chain:SENTRY

Blockchain Forensics & Investigative Intelligence Workbench

Platform Roadmap

CONFIDENTIAL — FOR EXECUTIVE AND ENGINEERING REVIEW

Version 2.0  |  August 2026

# Executive Summary

ChainSentry is a blockchain-forensics workbench for commercial-crime and cyber investigators. Its investigative capability is verified: risk scoring, layered sanctions screening, attribution across 78 chains, case intake with evidence processing, transaction graphs, fund-flow tracing to an exchange endpoint, infrastructure and ransomware context, monitoring, case-quality scoring and cited dossier composition.

This roadmap sets the sequence by which that capability becomes a supported product. It is a roadmap only: phases, milestones, dependencies, ownership and gates. Operational, release, incident and pilot-operations procedures are deliberately out of scope and are held in the companion operational plan.

The programme position changed materially on 19 August 2026. Twelve implementation gaps — every Critical and Must item in the specification gap register — are now closed in the codebase and verified against a recorded baseline. What blocks a pilot is no longer engineering capability.

Programme Position - Capability: sufficient for a pilot. The investigative workflow completes end to end. - Implementation: every Critical and Must gap closed on a review branch, verified by build, test and static analysis against a pre-change baseline. - Deployment: unchanged. None of the closed work is serving. The running build is forty days and twenty-nine commits behind the trunk. - Blocking: supplier-credential rotation, which has not happened, and a controlled release that must be reconstructed file by file rather than from a commit range. - Watch item: the development trunk stubs an address-security integration that is live on the deployment, so an unconsidered release would close twelve gaps and regress a screening layer in the same act.

The roadmap therefore opens with Phase 0, whose sole purpose is to make the closed work real and the known exposure shut. Phases 1 to 3 follow the sequence established in the product specification: pilot readiness, controlled pilot, productisation, then capability expansion.

Table of Contents

Executive Summary	2

1. Planning Basis & Governance	5

1.1 Verified Starting Point	5

1.2 Scope of This Roadmap	6

1.3 Prioritisation Model	6

1.4 Governance and Decision Rights	6

1.5 How This Roadmap Is Maintained	7

2. MVP Readiness Assessment	8

2.1 Method	8

2.2 Readiness Score	8

2.3 What Each Phase Is Worth	8

2.4 What Is Already MVP-Grade	9

2.5 Gaps to Close for MVP Readiness	10

2.6 Assessment Boundaries	10

3. Integrated Roadmap	11

3.1 Roadmap at a Glance	11

3.2 Phase 0 — Land & Secure (Days 0–5)	11

3.4 Phase 1B — Controlled Pilot (Weeks 5–8)	12

3.5 Phase 2 — Productisation (Months 3–5)	12

3.7 Parallel Workstreams	13

3.8 Explicitly Not on the Roadmap	13

4. Milestones, Dependencies & Critical Path	15

4.1 Milestone Register	15

4.2 The Critical Path	15

4.3 Dependency Matrix	15

4.4 Sequencing Rules	16

4.5 Schedule Risks	16

5. Delivery Plan & Workstreams	17

5.1 Workstream Register	17

5.2 Ownership	17

5.3 Indicative 30 / 60 / 90-Day Shape	17

5.4 Backlog Governance	17

5.5 Capacity Considerations	17

5.6 Phase Evidence Packs	18

6. Measurement & Phase Gates	19

6.1 Programme Scorecard	19

6.2 Phase Gate Criteria	19

6.3 Gate Status at This Issue	19

6.4 Metric Integrity Rules	19

6.5 Escalation	20

7. Traceability	21

7.1 Closed Implementation Gaps Awaiting Deployment	21

7.2 Open Items by Phase	21

7.3 Specification Boundaries and Where They Are Addressed	22

8. Document Control	23

8.1 Control and Review	23

8.2 Version History	23

8.3 Approval Record	23

# 1. Planning Basis & Governance

## 1.1 Verified Starting Point

Every figure below was established by direct inspection rather than carried from a prior document. Where a claim is documentary it is labelled. This is the state the roadmap starts from, and it is the baseline against which progress is measured.

| Dimension | Position on 19 August 2026 | Basis |
| --- | --- | --- |
| Investigative surfaces | 26 page routes, 19 protected; 44 API handlers | Verified in source |
| Intelligence holdings | 583,574 tags across 527,026 addresses on 78 chains; 4,633 sanctioned addresses | Observed |
| Source roles | 12 of 18 operational; 6 degraded | Documentary |
| Accounts | 1 organisation, 6 accounts across 2 roles | Observed |
| Deployment identity | Basis commit plus 8 additive files; 43 uncommitted modifications | Observed |
| Deployment currency | 29 commits, roughly 40 days behind the trunk | Verified in source |
| Implementation gaps | 12 closed; 1 Should open; 2 future capability | Verified in source |
| Operational blockers | 2, both Critical: credential rotation and deployment parity | Observed |
| Quality gates | Repaired; 62 static type errors and 11 stale tests remain | Verified in source |
| Reachability | Private-network interface only; database on loopback | Observed |

## 1.2 Scope of This Roadmap

| In Scope | Out of Scope |
| --- | --- |
| Phases, their objectives, entry and exit criteria. | Operational runbooks and daily operating routines. |
| Milestones, dependencies and the critical path. | Release, change and configuration procedures. |
| Workstreams, ownership and decision rights. | Incident, security and continuity procedures. |
| Gates, measures and the evidence that closes each phase. | Pilot operations, onboarding and support handling. |
| Traceability from every roadmap item to a specification gap or boundary. | Definition of product capability, which belongs to the specification. |

The companion operational plan holds everything in the right-hand column. Where the two touch the same item they must agree; this document is authoritative on sequence, the specification on capability, and the operational plan on procedure.

## 1.3 Prioritisation Model

Work is ordered by what it unblocks, not by effort or by visibility. An item is scheduled earlier when a later item cannot safely proceed without it, when it removes an exposure whose window is already open, or when deferring it would force rework.

| Class | Definition | Scheduling Rule |
| --- | --- | --- |
| Blocker | A pilot cannot start, or cannot start safely, until this is done. | Phase 0 or early Phase 1. Nothing that depends on the outcome is scheduled in parallel. |
| Exposure | An unremediated risk whose window is already open. | Ahead of any work that widens reachability. Rotation before access, without exception. |
| Enabler | Unlocks a class of later work or removes a recurring cost. | Before the work it enables, never alongside it. |
| Completeness | Closes a documented gap between what is claimed and what happens. | Phase 1 or 2 by severity. |
| Expansion | New capability beyond the verified boundary. | Phase 3 only, after the pilot has reported. |

## 1.4 Governance and Decision Rights

| Decision | Owner | Consulted | Rule |
| --- | --- | --- | --- |
| Phase gate pass | Platform owner | Security, delivery lead, sponsor | Every exit criterion evidenced. A criterion is not waivable by assertion. |
| Release approval | Delivery lead | Platform operations, security | Requires a manifest, an ordered migration plan and a written verification plan. |
| Credential rotation sign-off | Security owner | Platform operations | Confirmed by changed masked fingerprints, never by a statement that keys were changed. |
| Scope change mid-phase | Platform owner | Delivery lead | Deferred to the next phase by default unless it is a defect or a blocker. |
| Accepting a residual risk | Platform owner | Security owner | Recorded with an owner and a review date. An unowned accepted risk is not accepted. |
| Phase 3 prioritisation | Platform owner | Pilot sponsor, investigators | Set from pilot evidence, not from assumption. |

## 1.5 How This Roadmap Is Maintained

- Re-issue after any material deployment, source-availability, scope or architecture change. A roadmap describing a superseded state is worse than none at all.

- Re-observe rather than carry forward. Any figure older than the last release is documentary until confirmed against the running system.

- Record deferrals. An item moved to a later phase carries a reason and an owner; it is never moved silently.

- Retire explicitly. An item that will not be done is closed as will-not-do rather than left to age.

- Keep documents reconciled. If a capability claim moves, the specification and this roadmap change in the same cycle.

# 2. MVP Readiness Assessment

This section answers one question: is ChainSentry ready to be used as an MVP by a named external investigator? It is scored rather than asserted, so the judgement can be argued with rather than merely accepted.

## 2.1 Method

Readiness is scored across eight dimensions, each weighted by how much it determines whether a pilot can proceed safely. Two scores are reported, and the distinction between them is the central finding of this assessment.

| Score | What It Measures | Why Both Are Needed |
| --- | --- | --- |
| Implementation readiness | What the codebase does today, on the review branch. | Shows whether the engineering work exists. |
| Deployed readiness | What the running instance actually serves. | Shows what a pilot user would meet. A capability that exists but is not deployed protects nobody. |

A single blended figure was deliberately not produced. It would average away the fact that most of the remediation is complete but none of it is serving, which is the most important thing a reader needs to know.

## 2.2 Readiness Score

| Dimension | Weight | Implementation | Deployed | Principal Constraint |
| --- | --- | --- | --- | --- |
| Core investigative capability | 20 | 95 | 95 | EVM-only tracing is a stated MVP boundary, not a defect. |
| Intelligence holdings & coverage | 10 | 70 | 80 | Six of eighteen source roles degraded. On the branch, two of four screening layers contribute nothing. |
| Security & authorisation | 20 | 80 | 30 | Deployed: unauthenticated diagnostic route, ungated fixtures, public documentation, unenforced audit, no real password change. |
| Evidence integrity & defensibility | 12 | 75 | 55 | No cryptographic signing. Deployed audit log is append-only by comment only. |
| Access & identity | 10 | 40 | 20 | No TLS access, no named accounts, only two of five roles exist. |
| Deployment & release integrity | 10 | 60 | 15 | Deployment is a basis commit plus eight files with forty-three uncommitted modifications; no migration ledger. |
| Reliability & recoverability | 10 | 30 | 30 | Backup never restored; no recovery objectives; no alerting on job staleness. |
| Quality gates & regression safety | 8 | 65 | 10 | Gates repaired on the branch; 62 type errors and 11 stale tests remain. |

Readiness Verdict - Implementation readiness: 69%. The engineering work for an MVP largely exists. - Deployed readiness: 47%. What a pilot user would actually meet today is materially less ready. - The 22-point gap is not a measurement artefact. It is twelve closed gaps sitting in a branch that has never been deployed. - Verdict: NOT MVP-ready for external use. It is close on capability and far on exposure — the two are not interchangeable, and capability does not compensate for an open credential exposure. - The single highest-leverage act is Phase 0. It writes almost no new code and moves deployed readiness from 47% to roughly 77%.

## 2.3 What Each Phase Is Worth

Readiness is not linear with effort. The largest single movement comes from deploying work that already exists.

| Milestone | Deployed Readiness | Movement | What Causes It |
| --- | --- | --- | --- |
| Today | 47% | — | Twelve gaps closed but undeployed; credentials unrotated. |
| After Phase 0 | 77% | +30 | Rotation closes the exposure; the release lands twelve closed gaps; migrations restore schema control. |
| After Phase 1 | 90% | +13 | TLS access, named accounts, enforcement across all handlers, isolation proven, sources dispositioned. |
| MVP threshold | 85% | — | The level at which external casework is defensible. Reached during Phase 1, not before. |

## 2.4 What Is Already MVP-Grade

It is as important to name what does not need work. These dimensions are not the constraint and should not absorb effort.

| Strength | Evidence |
| --- | --- |
| The investigative spine completes | Intake, triage, expansion, trace to an exchange endpoint, scorecard and cited report all function. Thirty-two of thirty-two authenticated paths returned live data. |
| The risk model is sound and now protected | Six factors weighted 30/20/15/15/12/8, five bands, sanctions override preserving the raw score. Fifteen deterministic tests were written against it and passed on first run. |
| The intelligence base is substantial and independent | 583,574 tags across 527,026 addresses on 78 chains and 4,633 sanctioned addresses, held locally rather than depending on per-query availability. |
| Performance is not a constraint | Screening and attribution under 20 ms; risk scoring 1.4–1.5 s warm; trace to cash-out about 32 seconds. |
| Degradation is honest | Source failure reduces enrichment depth and is surfaced, rather than being presented as a completed negative search. |

2.5 Gaps to Close for MVP Readiness

Ordered by what must happen first. The Blocking column states whether a pilot can proceed at all while the gap is open.

| # | Gap | Blocking | Action to Close | Phase |
| --- | --- | --- | --- | --- |
| 1 | Four supplier credentials served to unauthenticated callers remain unrotated. The deployment configuration predates the fix by a month. | YES | Revoke and reissue at the provider; update the deployment; verify by changed masked fingerprints. | 0 |
| 2 | The address-security integration is stubbed on the trunk but live on the deployment, so releasing would regress a screening layer. | YES | Restore the integration, or record the reduced screening in the manifest and the specification. | 0 |
| 3 | The deployment is not describable: a basis commit plus eight additive files carrying forty-three uncommitted modifications. | YES | Reconstruct the manifest file by file and approve it. | 0 |
| 4 | Backup has never been proven by restore, and no recovery objective exists. | YES | Rehearse a restore into an isolated target and verify by sampling, before any migration runs. | 0 |
| 5 | No migration ledger exists on the deployment; two migrations are pending, one of which must precede the application release. | YES | Apply the backfill then the audit migration through the runner; confirm the ledger. | 0 |
| 6 | Twelve closed implementation gaps are not serving, including an unauthenticated diagnostic route still live on the deployment. | YES | Deploy the release in a controlled window and run the verification sweep. | 0 |
| 7 | No TLS-terminated external access; the platform is reachable only on a private network interface. | YES | Provision TLS termination and correct the callback and session URL. | 1 |
| 8 | Only two of five roles exist, with six accounts and no named reviewer or auditor. | YES | Issue named per-person accounts, one role each. | 1 |
| 9 | Role enforcement covers the investigative listings but not every mutating handler. | YES | Extend enforcement; prove with per-role negative tests. | 1 |
| 10 | Organisation isolation has never been exercised with more than one organisation. | YES | Create a second organisation and run a cross-organisation negative test. | 1 |
| 11 | Six source roles are degraded, and two of four screening layers are impaired. | NO | Renew, replace or retire each; retest coverage. | 1 |
| 12 | No inventory proves that every pilot surface returns live rather than fixture data. | YES | Complete a surface-by-surface inventory with recorded results. | 1 |
| 13 | Boundaries are not acknowledged in writing by the sponsor. | NO | Written acknowledgement of EVM-only tracing, webhook-only alerting and MVP maturity. | 1 |
| 14 | 62 static type errors and 11 stale tests remain against now-blocking gates. | NO | Clear the debt so the gates can pass. | 2 |
| 15 | Oversight has no dedicated surface, and there is no batch screening or attachable export. | NO | Deliver investigator outputs with acceptance tests. | 2 |

Reading the Gap List - Ten of the fifteen gaps are blocking, and six of those close in Phase 0. - Only two of the fifteen require writing significant new application code. The rest are release, access and operational acts. - This is the shape of a product whose engineering is ahead of its operations, and it should be resourced accordingly. - The four non-blocking gaps are genuine and should not be forgotten, but none of them should delay a pilot.

## 2.6 Assessment Boundaries

- Scoring is judgement applied to evidence, not a measurement. The weights reflect what determines safe pilot exposure; a different reader may weight differently and should say so rather than adjusting the total quietly.

- The figures are point-in-time. Deployed readiness was assessed against the instance observed on 19 August 2026 and changes the moment a release lands.

- Capability was not re-tested end to end in this assessment; it draws on the recorded verification of thirty-two of thirty-two authenticated paths.

- The six degraded source roles are documentary rather than re-observed, so the intelligence dimension carries the widest uncertainty.

- Readiness is scored for a controlled pilot with named users, not for general availability, which is a materially higher bar.

# 3. Integrated Roadmap

## 3.1 Roadmap at a Glance

| Phase | Window | Objective | Exit Criterion |
| --- | --- | --- | --- |
| Phase 0 — Land & Secure | Days 0–5 | Close the open exposure and get twelve closed gaps onto the deployment safely. | Credentials reissued and verified; release deployed with migrations applied; post-release sweep clean. |
| Phase 1 — Pilot Readiness | Weeks 1–4 | Make verified capability reachable by named external users with roles enforced. | A partner investigator signs in over TLS with a named account and completes a case from intake to cited report on live data. |
| Phase 1B — Controlled Pilot | Weeks 5–8 | Run real casework with a small named cohort and learn from it. | Pilot exit criteria met; defects triaged; continuation decision recorded. |
| Phase 2 — Productisation | Months 3–5 | Make the platform supportable by people who did not build it. | Managed migrations, evidenced recoverability, monitoring, second-organisation isolation, residual quality debt cleared. |
| Phase 3 — Capability Expansion | Month 6+ | Extend the investigative boundary where the pilot showed it costs time. | Non-EVM tracing in production; dossier signing; bridge continuation with provenance. |

## 3.2 Phase 0 — Land & Secure (Days 0–5)

Phase 0 exists because twelve gaps are closed in a branch that is not deployed, and because an exposure that has already occurred is still open. It adds no capability and takes no new scope. It ends when the current work is running and the exposure is shut.

| Attribute | Definition |
| --- | --- |
| Objective | Make the closed work real, and close the credential exposure before reachability widens. |
| In scope | Rotation, regression decision, manifest, restore rehearsal, migrations, deployment, verification. |
| Out of scope | Any new capability, any new surface, any change not required to land existing work. |
| Entry criteria | Review branch verified against a recorded baseline: build passes, tests no worse, type debt reduced. |
| Exit criteria | All seven deliverables evidenced; post-release sweep clean; no S1 open. |
| Primary risk | Deploying the trunk unresolved regresses the address-security screening layer. |

| # | Deliverable | Owner | Exit Evidence |
| --- | --- | --- | --- |
| 0.1 | Revoke and reissue the four supplier credentials served to unauthenticated callers; update deployment configuration. | Security owner | Four changed fingerprints in masked key-health output; old values rejected by the providers. |
| 0.2 | Resolve the address-security regression: restore the integration, or record the reduced screening in the manifest and the specification. | Engineering | A written decision, and a screening-layer count that matches what the product claims. |
| 0.3 | Reconstruct the release manifest file by file. | Delivery lead | Manifest listing every file, its origin and destination state, approved by a named owner. |
| 0.4 | Take a full backup of database and evidence volumes and prove it restores into an isolated target. | Platform operations | Restore verified by sampling cases, evidence, attribution, sanctions and audit rows. |
| 0.5 | Apply the organisation backfill migration, then the audit-enforcement migration, through the migration runner. | Platform operations | Ledger records both; no investigation left without an organisation, or the residue explained. |
| 0.6 | Deploy the application release in a controlled window with a named rollback trigger. | Delivery lead | Deployment recorded; rollback plan on file and unused. |
| 0.7 | Run the post-release verification sweep, including anonymous probes of the removed diagnostic route and the gated documentation tree. | Platform operations | Recorded results; diagnostic route returns not-found; documentation requires a session. |

Phase 0 Sequencing Is Not Negotiable - Rotation precedes any widening of reachability. The exposure window is already open; making the platform easier to reach before closing it inverts the risk. - Backup and verified restore precede the migrations. A migration that has never been rehearsed against a restorable copy is an untested change to persistent evidence. - The organisation backfill precedes the application release. If role-aware retrieval reaches users first, records without an organisation are visible only to their owners and a reviewer sees an incomplete list. - Nothing in Phase 1 begins until the post-release sweep is clean.

3.3 Phase 1 — Pilot Readiness (Weeks 1–4)

Goal: a named external investigator reaches the platform securely, acts under an enforced role, and produces a defensible output on live data. Every item is a prerequisite for exposure rather than an improvement to it.

| Attribute | Definition |
| --- | --- |
| Objective | Make verified capability safely reachable by named external users. |
| In scope | Access, identity, authorisation completion, isolation, data-truth inventory, source disposition, boundary setting. |
| Out of scope | New investigative capability; anything deferred to productisation. |
| Entry criteria | Phase 0 evidence pack closed. |
| Exit criteria | The pilot gate in Section 5.2 passed on evidence. |
| Primary risk | Issuing oversight accounts before role enforcement is complete, which grants a label rather than access control. |

| # | Workstream | Deliverable | Exit Evidence |
| --- | --- | --- | --- |
| 1.1 | Access | TLS-terminated external access with corrected callback and session URL. | End-to-end sign-in from the pilot network, not from the host. |
| 1.2 | Identity | Named per-person accounts across administrator, investigator, reviewer and auditor. | Every action attributable to a person; no shared credentials in use. |
| 1.3 | Authorisation | Role enforcement extended from the investigative listings to the remaining mutating handlers. | Per-role negative tests: each role refused what its matrix row denies. |
| 1.4 | Isolation | A second organisation created and cross-organisation retrieval tested. | A two-organisation negative test, which has never been run. |
| 1.5 | Data truth | Every pilot surface confirmed to return live or explicitly labelled unavailable data. | Surface inventory with the result recorded against each entry. |
| 1.6 | Source health | Six degraded roles renewed, replaced or retired; anonymised transport confirmed. | Health surface free of unexplained degradation; dossier coverage retested. |
| 1.7 | Boundaries | Written statement of EVM-only tracing, webhook-only alerting, two risk models and MVP maturity. | Acknowledged by the pilot sponsor before accounts are issued. |

## 3.4 Phase 1B — Controlled Pilot (Weeks 5–8)

A small cohort performs real casework under observation. The purpose is to find where the product fails a working investigator, not to demonstrate that it renders.

| Attribute | Definition |
| --- | --- |
| Objective | Learn from real casework inside the verified boundary. |
| Cohort | A small number of named investigators plus at least one supervising reviewer, so the oversight path is exercised rather than assumed. |
| Scope | Real cases within the verified boundary: EVM tracing, webhook alerting, no external API integration. |
| Entry criteria | Pilot gate passed; support path exercised with a seeded defect. |
| Exit criteria | Pilot exit criteria in Section 6.2 met; continuation decision recorded. |
| Guardrail | Any finding that a pilot surface returned fixture or stale data as intelligence is a Severity 1 event and pauses the pilot. |

## 3.5 Phase 2 — Productisation (Months 3–5)

Phase 2 makes the platform supportable by people who did not build it. It is the phase most often skipped and the most expensive to skip.

| Theme | Deliverables | Why It Matters |
| --- | --- | --- |
| Engineering foundations | Blocking gates sustained; residual 62 type errors and 11 stale tests cleared; the migration ledger adopted as the only path to schema change. | Continuous integration was dead for five weeks because a lockfile drifted. A gate only protects a release if it can run. |
| Recoverability | Documented backup set, rehearsed restore, defined recovery objectives, known rollback boundaries. | The platform holds cases, evidence and audit state. Recovery cannot first be attempted during an incident. |
| Observability | Structured logging keyed by correlation identifier; alerting on provider degradation and job staleness. | Source health is visible in-product but nothing pages anyone. Datasets once ran 23 days stale unnoticed. |
| Secret governance | Managed secret storage replacing plain environment values; rotation cadence with a named owner. | Credentials currently reach the container as environment values readable from container metadata. |
| Access maturity | Enforcement across every handler; organisation columns promoted to non-nullable once write paths are verified; per-organisation quotas. | Enforcement currently covers the listings; the columns stay nullable for one deliberate cycle. |
| Risk-model convergence | One scoring model, or two with a documented reason for each and labelled output throughout. | Two models currently produce different scores for the same address. Labelling is honesty; convergence is resolution. |
| Investigator outputs | Batch screening, attachable signed or hashed report export, dedicated auditor activity view. | The one implementation gap still open. Oversight has no dedicated surface. |
| Product completeness | Email alert delivery, entity-name sanctions search, explicit chain override, mixer threshold configuration. | Each closes a boundary the specification currently has to state as a limitation. |

3.6 Phase 3 — Capability Expansion (Month 6+)

Expansion is scheduled only after the pilot has reported. Building beyond the verified boundary before knowing where investigators actually stall is how effort is misallocated.

| Capability | Value | Precondition |
| --- | --- | --- |
| Bitcoin and non-EVM tracing | Closes the largest gap between attribution reach and tracing reach. Attribution covers 78 chains; tracing covers one family. | Chain-specific trace providers and explicit chain selection. |
| Cross-chain bridge following | Closes a common evasion route that today requires manual continuation. | A provenance model that survives a hop between networks. |
| Cryptographic dossier signing | Completes the step from integrity digest toward formal evidentiary use. | Key custody and verification tooling, not merely a signature field. |
| Real-time streaming ingestion | Moves monitoring beyond a fifteen-minute evaluation cycle. | Phase 2 observability; streaming without alerting is noise. |
| Messaging-channel alerts | Completes the notification matrix that Phase 2 opens with email. | Phase 2 delivery framework. |
| Case collaboration and assignment | Supports multi-investigator teams rather than single-owner cases. | Role enforcement complete across all handlers. |
| Saved searches and watchlists | Supports recurring monitoring programmes. | Quota control, so a saved search cannot exhaust a metered source. |
| Self-service organisation onboarding | Enables scale beyond a small number of organisations. | Two-organisation isolation proven in Phase 1. |

## 3.7 Parallel Workstreams

Next-Generation Investigation Experience - Working prototype of sixteen additive page routes. Not part of the pilot and excluded from the verified surface count. - A case opens as a board; investigators pin findings with capture timestamps, intended to assemble into a structured report. - Its presence establishes no backend contract. No pilot exit criterion depends on it. - Phase 2: confirm direction from pilot feedback, persist pins with provenance, bring it under the same role enforcement as the rest of the platform. - Phase 3: support large cases and adopt progressively. It replaces current surfaces only when it can carry full provenance.

Dark-Web Intelligence Source - A separate collector. Not part of the pilot and not a dependency of any pilot exit criterion. - Verified contribution: 1,790 new addresses with source, context and first-seen date, remediated to fully checksum-verified addresses before integration. - Observations must be labelled as observed on the dark web. An observation is not an attribution, and neither is a criminal designation. - Depends on the anonymised-network provisioning in Phase 1; until proxy configuration reaches the container the capability contributes nothing. - Phase 2: graded-confidence ingestion, curation and scheduled refresh. Phase 3: live dossier lookup.

## 3.8 Explicitly Not on the Roadmap

Recording what is excluded prevents it from reappearing as an assumption.

| Excluded | Reason |
| --- | --- |
| A public API contract with issued keys | No implemented external contract exists. The in-product reference described endpoints that do not exist; it now documents the session-authenticated routes that do. A published contract is a Phase 3 decision, not an assumed deliverable. |
| Autonomous investigative conclusions | The platform drafts, organises and explains. A criminal designation remains a human judgement, and no roadmap item changes that. |
| Multi-region or high-availability topology | Single-host deployment is adequate through productisation. Revisit only when organisation count justifies it. |
| Replacing the current interface with the prototype | The next-generation experience is additive until it can carry full provenance. No phase commits to a cutover. |

# 4. Milestones, Dependencies & Critical Path

## 4.1 Milestone Register

| ID | Milestone | Phase | Definition of Done |
| --- | --- | --- | --- |
| M1 | Exposure closed | 0 | Four credentials reissued; changed fingerprints verified; providers reject the old values. |
| M2 | Regression decision made | 0 | Address-security integration restored, or reduced screening recorded in manifest and specification. |
| M3 | Deployment describable | 0 | Manifest reconstructed file by file and approved by a named owner. |
| M4 | Recovery proven | 0 | Restore into an isolated target verified by sampling cases, evidence, attribution, sanctions and audit. |
| M5 | Schema under control | 0 | Both migrations applied through the runner; ledger confirms; backfill residue explained. |
| M6 | Closed work serving | 0 | Release deployed; verification sweep clean; diagnostic route returns not-found. |
| M7 | Externally reachable | 1 | Sign-in over TLS from the pilot network with a corrected session URL. |
| M8 | Roles real | 1 | Named accounts across four roles; per-role negative tests recorded. |
| M9 | Isolation proven | 1 | Two-organisation negative test passed. |
| M10 | Sources dispositioned | 1 | Every degraded role renewed, replaced or retired; no unexplained degradation. |
| M11 | Pilot gate passed | 1 | All nine gate criteria evidenced; go decision recorded. |
| M12 | Pilot reported | 1B | Exit criteria assessed; continuation decision recorded with rationale. |
| M13 | Supportable | 2 | Recoverability, observability, secret governance and quality debt complete. |
| M14 | Boundary extended | 3 | Non-EVM tracing in production with provenance. |

## 4.2 The Critical Path

The critical path runs M1 through M7. Everything else can be parallelised; nothing on this chain can, because each link changes the safety or the validity of the next.

| Step | Milestone | Why It Cannot Move |
| --- | --- | --- |
| 1 | M1 Exposure closed | Widening reachability before closing a known exposure inverts the risk. The private-network boundary is currently the only containment. |
| 2 | M2 Regression decision | The manifest cannot describe the release honestly until the screening question is answered. |
| 3 | M3 Deployment describable | No release can be verified against a deployment that no artefact describes. |
| 4 | M4 Recovery proven | Migrations alter persistent evidence. An unrehearsed restore is not a rollback plan. |
| 5 | M5 Schema under control | Role-aware retrieval against records with no organisation shows a reviewer an incomplete list. |
| 6 | M6 Closed work serving | Phase 1 verifies behavior that exists only in the new build. Testing the old build proves nothing. |
| 7 | M7 Externally reachable | Every pilot activity depends on a participant being able to reach the platform at all. |

## 4.3 Dependency Matrix

| Predecessor | Successor | Nature | Consequence If Inverted |
| --- | --- | --- | --- |
| Credential rotation | TLS external access | Hard | A known exposure moves from a private network to the internet. |
| Regression decision | Release manifest | Hard | The manifest asserts a screening depth the build does not provide. |
| Restore rehearsal | Migration application | Hard | A schema change to evidence with no proven way back. |
| Organisation backfill | Application release | Hard | Six cases become visible only to their owners; a reviewer concludes cases are missing. |
| Application release | All Phase 1 verification | Hard | Phase 1 tests a build that will not be the pilot build. |
| Role enforcement complete | Reviewer and auditor accounts | Hard | Oversight accounts carry a label without access control. |
| Isolation test | Any second organisation | Hard | Cross-organisation exposure in a product whose value is evidential integrity. |
| Source disposition | Pilot start | Soft | A permanent degradation banner trains users to ignore warnings. |
| Pilot feedback | Phase 3 scope | Soft | Expansion built against assumption rather than observed friction. |
| Quality debt cleared | Sustained gate enforcement | Soft | Gates stay red, and teams learn to route around them. |

## 4.4 Sequencing Rules

Five rules govern this roadmap. Each exists because inverting it causes a specific, identified harm rather than merely being untidy.

| Rule | Rationale |
| --- | --- |
| Rotation before reachability | An exposure already occurred. Making the platform easier to reach before closing it increases the population that can exploit it. |
| Backup and restore before schema change | Migrations alter persistent evidence that cannot be regenerated. |
| Backfill before role-aware retrieval reaches users | Otherwise legacy records lose visibility and the loss looks like data loss. |
| Enforcement before oversight accounts | A role that is not enforced is a label, and issuing it creates a false assurance of separation of duties. |
| Deploy before verifying | Verification against a build that will not be the pilot build produces evidence about nothing. |

## 4.5 Schedule Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Phase 0 treated as administrative overhead and compressed | High | Every later phase rests on invalid ground | Phase 0 has its own gate and evidence pack; no Phase 1 item starts before it closes. |
| One person holds both platform-operations and security roles | Medium | Phase 0 is sequential, so a five-day window becomes considerably longer | Assess role coverage before committing to a pilot date. |
| Release deferred while capability work continues | Medium | The deployment gap widens and the manifest becomes harder to reconstruct | Deployment currency is a reported measure with a target of zero at release. |
| Scope added during the pilot | High | The pilot learns less and exits without a decision | Scope change is a platform-owner decision, deferred by default. |
| Quality gates bypassed under delivery pressure | Medium | A repeat of the five-week continuous-integration outage | Gate status reported at every phase gate; the install step is itself a gate. |
| Phase 3 prioritised from assumption | Medium | Effort spent on the wrong boundary | Phase 3 scope is set from pilot evidence, and is not fixed in this document. |

# 5. Delivery Plan & Workstreams

## 5.1 Workstream Register

| ID | Workstream | Scope | Phases |
| --- | --- | --- | --- |
| WS-1 | Security & Credentials | Rotation, exposure response, secret governance, audit enforcement. | 0, 2 |
| WS-2 | Release & Deployment | Manifest, migration control, deployment, verification sweeps. | 0, 1, 2 |
| WS-3 | Access & Identity | TLS access, named accounts, role enforcement, organisation isolation. | 1, 2 |
| WS-4 | Intelligence Sources | Degraded-role disposition, transport provisioning, health alerting. | 1, 2 |
| WS-5 | Quality Engineering | Gate enforcement, residual type debt, stale tests, regression coverage. | 1, 2 |
| WS-6 | Operability | Backup and restore, monitoring, structured logging, recovery objectives. | 0, 2 |
| WS-7 | Product Completeness | Investigator outputs, alert delivery, entity-name search, model convergence. | 2 |
| WS-8 | Capability Expansion | Non-EVM tracing, bridges, signing, streaming. | 3 |

## 5.2 Ownership

| Activity | Responsible | Accountable | Consulted |
| --- | --- | --- | --- |
| Credential rotation | Security owner | Platform owner | Platform operations |
| Regression decision | Engineering | Platform owner | Security |
| Release manifest & deployment | Delivery lead | Platform owner | Platform operations, security |
| Migration application | Platform operations | Delivery lead | Engineering |
| Restore rehearsal | Platform operations | Platform owner | Engineering |
| Role enforcement | Engineering | Delivery lead | Security |
| Isolation testing | Engineering | Delivery lead | Security |
| Source disposition | Intelligence-source owner | Platform owner | Engineering |
| Phase gate pass | Platform owner | Platform owner | Security, delivery, sponsor |

## 5.3 Indicative 30 / 60 / 90-Day Shape

| Window | Focus | Completion Signal |
| --- | --- | --- |
| Days 0–5 | Rotate; decide the regression; build the manifest; rehearse restore; apply migrations; deploy; verify. | Twelve closed gaps are serving and the exposure is shut. M1–M6. |
| Days 6–30 | TLS access, named accounts, enforcement across handlers, isolation test, source disposition, boundary acknowledgement. | Pilot gate assessed on evidence; go or no-go recorded. M7–M11. |
| Days 31–60 | Controlled pilot with a named cohort including a reviewer; weekly review; defect triage. | Pilot exit criteria assessed; continuation decision recorded. M12. |
| Days 61–90 | Productisation opens: recoverability, observability, secret governance, quality debt, investigator outputs. | Platform supportable by someone who did not build it. Progress toward M13. |

Windows are indicative, not commitments. Phase 0 is sequential and its duration depends on role coverage rather than on effort; see the schedule risks in Section 4.5.

## 5.4 Backlog Governance

- Single register: one backlog carries implementation gaps, operational blockers, defects and enhancements. Parallel lists diverge and then disagree.

- Closure requires evidence: an item closes when its exit evidence exists, not when a change is merged. Closed in code and closed in production are recorded separately.

- No silent descoping: an item removed from a phase is recorded as deferred with a reason and an owner.

- Defects outrank enhancements within a phase, and a correctness defect outranks a usability defect.

- Ageing is visible: a blocker open beyond its phase window is escalated at the next gate rather than rolled forward.

## 5.5 Capacity Considerations

This roadmap does not assert a team size, which would be a guess presented as a plan. It states the distinct capabilities the sequence requires, so resourcing can be assessed honestly against them.

| Capability Required | Where It Is Load-Bearing |
| --- | --- |
| Platform operations | Phase 0 throughout: deployment, migrations, restore rehearsal, verification sweeps. |
| Security ownership | Rotation, exposure response, secret governance, access review. |
| Application engineering | Enforcement completion, residual quality debt, investigator outputs, model convergence. |
| Intelligence-source ownership | Degraded-role disposition, transport provisioning, ongoing supplier health. |
| Delivery coordination | Manifest discipline, gate evidence, backlog governance. |
| Investigative domain input | Acceptance testing, pilot feedback interpretation, Phase 3 prioritisation. |

The Principal Capacity Risk - Phase 0 concentrates platform-operations and security work into five days, and its steps are sequential rather than parallel. - If one person holds both roles, the window is not five days, and the pilot date derived from it will be wrong. - Assess role coverage before committing to a date. This is the largest schedule risk in the roadmap.

## 5.6 Phase Evidence Packs

Each phase closes with an evidence pack so that a reviewer who was not present can confirm it actually completed.

| Artefact | Phase | Contents |
| --- | --- | --- |
| Credential record | 0 | Rotation date, owner, masked fingerprints before and after, provider confirmation. |
| Regression decision | 0 | The decision, its rationale, and the resulting screening-layer claim. |
| Release manifest | 0 | Files, origins, destination state, approver, window, rollback trigger. |
| Recovery record | 0 | Backup timestamp, restore target, sampled rows verified. |
| Migration record | 0 | Ledger entries with checksums, durations, outcomes; residue explained. |
| Verification sweep | 0, 1 | Authenticated results, risk-band checks, anonymous probes of formerly exposed paths. |
| Access record | 1 | Accounts issued, roles assigned, per-role negative test results. |
| Isolation record | 1 | Two-organisation negative test method and outcome. |
| Gate record | All | Each exit criterion, its evidence, and the named approver. |

# 6. Measurement & Phase Gates

## 6.1 Programme Scorecard

Six measures, chosen because each would change a decision. A measure that cannot change a decision is reporting overhead.

| Measure | Definition | Today | Target at Pilot |
| --- | --- | --- | --- |
| Deployed readiness | Weighted readiness of the running instance, per Section 2. | 47% | 85% or above |
| Deployment currency | Commits between the deployment and the trunk. | 29 | Zero at release; never beyond one cycle |
| Exposure age | Days any known unremediated exposure has been open. | Open since the handler fix | Zero |
| Gap closure deployed | Implementation gaps closed and serving, not merely closed in code. | 0 of 12 | 12 of 12 |
| Source availability | Operational roles as a share of integrated roles. | 12 of 18 | No role degraded without a recorded disposition |
| Recoverability | Days since a verified restore rehearsal. | Never performed | Within one month, always |

## 6.2 Phase Gate Criteria

A gate is passed on evidence. A criterion is either evidenced or it is not; there is no partial credit and no waiver by assertion.

| Gate | Criteria | Status |
| --- | --- | --- |
| Phase 0 exit | Credentials reissued and verified. Regression decision recorded. Manifest approved. Restore verified by sampling. Both migrations applied and in the ledger. Release deployed. Verification sweep clean, including anonymous probes. | Not started |
| Pilot go / no-go | Phase 0 pack closed. TLS sign-in from the pilot network. Named accounts, one role each. Per-role negative tests recorded. Two-organisation isolation passed. Live-data inventory complete. Degraded sources dispositioned. Support path exercised. Boundaries acknowledged in writing. | 0 of 9 met |
| Pilot exit | Spine completed on real casework. A reviewer closed a case they did not create. No Severity 1 outstanding. Operational signals held. Boundaries understood by participants. Feedback triaged into the backlog. A restore rehearsed during the window. | Not applicable |
| Productisation exit | Recoverability, observability and secret governance complete. Enforcement across every handler. Organisation columns non-nullable. Quality debt cleared. Investigator outputs delivered. Risk models converged or documented. | Not applicable |

## 6.3 Gate Status at This Issue

| Gate | Criteria Count | Met | Blocking Item |
| --- | --- | --- | --- |
| Phase 0 exit | 7 | 0 | Credential rotation has not begun; no release has been built. |
| Pilot go / no-go | 9 | 0 | Every criterion depends on Phase 0 completing first. |
| Pilot exit | 7 | — | Pilot not started. |
| Productisation exit | 6 themes | — | Follows the pilot. |

## 6.4 Metric Integrity Rules

- State the basis. "Verified in source" and "observed on the deployment" are different claims and are never merged into one figure.

- Distinguish closed from deployed. The scorecard reports the deployed state; the backlog may report both, labelled.

- No silent caps. If a measure is sampled or bounded, the bound is stated. A sweep of part of a surface is never reported as a sweep of the surface.

- Missing is not zero. An absent measurement is reported as absent; absent evidence and evidence of absence are different.

- Label carried figures. Any number taken from an earlier document is documentary until re-observed.

## 6.5 Escalation

| Trigger | Escalate To | Within |
| --- | --- | --- |
| A Severity 1 incident | Platform owner and security owner | Immediately |
| A blocker open beyond its phase window | Platform owner | Next stand-up |
| A gate criterion proposed for waiver | Platform owner | Before the gate |
| A degraded source with no disposition for two cycles | Platform owner | Weekly review |
| A residual risk proposed for acceptance | Platform owner and security owner | Before acceptance is recorded |
| Scope change requested during a phase | Platform owner | Same week |

# 7. Traceability

Every roadmap item traces to a gap or a boundary recorded in the MVP Product Specification, so the two documents cannot drift apart without it being visible.

## 7.1 Closed Implementation Gaps Awaiting Deployment

| Specification Item | Closed By | Reaches Users At |
| --- | --- | --- |
| Unauthenticated diagnostic route | Route deleted; surviving deep-trace routes session-gated. | Phase 0 release |
| Authorisation enforcement | Role-aware retrieval on investigative listings. | Phase 0 release; completed in Phase 1 |
| Retrieval scope and oversight | Organisation scope with role-aware filters, behind an organisation backfill. | Phase 0 release, after the backfill |
| Live-versus-demo boundary | Fixture-backed tools refuse to run outside demonstration mode. | Phase 0 release |
| Inert administrative controls | Real server-side password change, both outcomes audited. | Phase 0 release |
| Public documentation exposure | Documentation tree gated; both inaccurate pages corrected. | Phase 0 release |
| Risk-model reconciliation | Dossiers name the model that produced their figure. | Phase 0 release; convergence in Phase 2 |
| Schema migration control | Migration runner with checksum ledger and drift detection. | Phase 0, applying its own migrations |
| Audit enforcement | Append-only enforced by trigger; retention through a self-logging function. | Phase 0 release |
| Automated quality gates | Blocking gates; test job; deterministic risk-model coverage. | Already in effect on the branch |
| Integration and transport health | Proxy variables passed through the runtime composition. | Phase 0 release; disposition in Phase 1 |
| Alert delivery honesty | Undeliverable channels withheld from the rule form. | Phase 0 release; delivery in Phase 2 |

## 7.2 Open Items by Phase

| Item | Class | Phase | Why Then |
| --- | --- | --- | --- |
| Supplier credential rotation | Exposure | 0 | The window is already open and no code change closes it. |
| Address-security regression decision | Blocker | 0 | The manifest cannot be honest until it is made. |
| Deployment parity | Blocker | 0 | Nothing else is valid until the deployment is describable. |
| Recovery rehearsal | Blocker | 0 | Migrations alter evidence; an unrehearsed restore is not a rollback plan. |
| TLS external access | Blocker | 1 | Every pilot activity depends on reachability. |
| Named accounts across four roles | Blocker | 1 | Actions must be attributable to a person. |
| Role enforcement across remaining handlers | Completeness | 1 | Required before oversight accounts are issued. |
| Two-organisation isolation test | Blocker | 1 | Never executed; required before any second organisation. |
| Degraded source disposition | Completeness | 1 | A permanent degradation banner trains users to ignore it. |
| Live-data surface inventory | Blocker | 1 | A pilot user must never meet fixture content as intelligence. |
| Investigator outputs | Completeness | 2 | The one implementation gap still open; oversight has no surface. |
| Recoverability and observability | Enabler | 2 | Makes the platform supportable by people who did not build it. |
| Secret governance | Enabler | 2 | Replaces plain environment values readable from container metadata. |
| Risk-model convergence | Completeness | 2 | Labelling is honesty; convergence is resolution. |
| Residual quality debt | Enabler | 2 | 62 type errors and 11 stale tests against now-blocking gates. |
| Non-EVM tracing | Expansion | 3 | Largest gap between attribution reach and tracing reach. |
| Bridge continuation | Expansion | 3 | Common evasion route requiring manual continuation today. |
| Dossier signing | Expansion | 3 | Completes the step from digest toward evidentiary use. |

## 7.3 Specification Boundaries and Where They Are Addressed

| Stated Boundary | Roadmap Response |
| --- | --- |
| Tracing and monitoring are EVM-compatible-chain focused. | Phase 3: chain-specific trace providers, beginning with Bitcoin. |
| Dossiers are digest-protected but not cryptographically signed. | Phase 3: signing with key custody and verification tooling. |
| Alert delivery is webhook-only. | Phase 2: email delivery, then messaging channels. |
| Sanctions free-text search matches addresses only. | Phase 2: entity-name search requires a schema change. |
| Cross-chain bridge activity requires manual continuation. | Phase 3: controlled bridge-hop continuation with provenance. |
| Multi-organisation separation is modelled but not exercised. | Phase 1: two-organisation isolation test, then quotas in Phase 2. |
| The content-security policy permits inline script execution. | Phase 2: nonce-based policy. |
| Two risk models are in use. | Phase 2: convergence, or documented retention of both with labelled output. |
| Enrichment is request-time or scheduled rather than streaming. | Phase 3: streaming ingestion, after Phase 2 observability. |

# 8. Document Control

## 8.1 Control and Review

| Attribute | Value |
| --- | --- |
| Document | ChainSentry Platform Roadmap |
| Version | 2.0 |
| Scope | Roadmap only: phases, milestones, dependencies, workstreams, gates, traceability, and the MVP readiness assessment. |
| Basis | Implementation source and the deployment observed on 19 August 2026 |
| Companion — capability | ChainSentry MVP Product Specification v4.1, authoritative on what the platform does |
| Companion — procedure | ChainSentry Roadmap & Operational Plan, holding operational, release, incident and pilot-operations procedures |
| Review trigger | Any material deployment, source-availability, scope or architecture change |
| Mandatory review | At every phase gate |

## 8.2 Version History

| Version | Date | Notes |
| --- | --- | --- |
| 2.0 | August 2026 | Rebuilt against the state verified on 19 August 2026 and reissued in the MVP specification format. Scope narrowed to the roadmap itself; operational, release, incident and pilot-operations procedures moved to the companion operational plan. Adds an MVP readiness assessment scoring implementation at 69% and the deployment at 47%, and Phase 0 — Land & Secure, because twelve implementation gaps are closed in a branch that is not deployed while a credential exposure remains open. Adds an explicit critical path, a milestone register, sequencing rules with their rationale, and traceability from every item to a specification gap or boundary. |
| 1.1 | August 2026 | Combined roadmap and operational plan. Written before the specification-to-implementation review and therefore planned against a state that no longer holds. |

## 8.3 Approval Record

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Platform owner |  |  |  |
| Delivery lead |  |  |  |
| Security owner |  |  |  |
| Pilot sponsor |  |  |  |

This roadmap is a point-in-time baseline. Readiness figures and any measure marked as observed were true of the deployment on 19 August 2026 only, and change the moment a release lands. Re-verify before treating them as current.