R.I.S.I.K

AI Platform Development & Operationalisation Programme

Detailed Analytical Cost Structure

| Total Programme Value | RM5,000,000 |
| --- | --- |
| Programme Duration | 12 Months |
| Delivery Model | Framework + IP + AI Engineering + Productisation + Deployment |
| Document Purpose | Costing, funding justification and programme governance |

Prepared for management, programme funding and technical-commercial evaluation

August 2026

# Document Structure

| Section | Content |
| --- | --- |
| 1 | Executive Summary |
| 2 | Costing Principles and Analytical Basis |
| 3 | Consolidated RM5.0 Million Cost Structure |
| 4 | R.I.S.I.K Framework & IP Development |
| 5 | AI Engineering & Intelligence Capability Development |
| 6 | Dedicated 7-Person Development Team |
| 7 | AI Infrastructure, Tooling & Development Environment |
| 8 | Data, Integration & Production Deployment |
| 9 | Cybersecurity, AI Assurance & Validation |
| 10 | Training, Knowledge Transfer & Documentation |
| 11 | Programme Governance, IP, Legal & Administration |
| 12 | Technical / Programme Contingency |
| 13 | 12-Month Cost Phasing |
| 14 | Cost-to-Deliverable Traceability |
| 15 | Cost Governance, Controls and Acceptance |
| 16 | Conclusion and Funding Position |

# 1. Executive Summary

This document presents a structured analytical cost model for a RM5.0 million, 12-month R.I.S.I.K AI Platform Development and Operationalisation Programme. The costing deliberately separates intellectual property creation, AI engineering, dedicated delivery manpower, tooling and infrastructure, production integration, assurance, knowledge transfer, governance and contingency. This structure is intended to support management approval, commercial proposal development, technical evaluation and funding justification.

Core funding position The RM5.0 million should be positioned as an investment in the creation and operationalisation of a reusable AI-enabled strategic intelligence capability, not as a conventional software-development fee.

| Cost Component | Amount | Share |
| --- | --- | --- |
| 1. R.I.S.I.K Framework & IP Development | RM750,000 | 15% |
| 2. AI Engineering & Intelligence Capability Development | RM900,000 | 18% |
| 3. Dedicated Development Team - 7 Personnel / 12 Months | RM1,800,000 | 36% |
| 4. AI Infrastructure, Tooling & Development Environment | RM550,000 | 11% |
| 5. Data, Integration & Production Deployment | RM450,000 | 9% |
| 6. Cybersecurity, AI Assurance & Validation | RM200,000 | 4% |
| 7. Training, Knowledge Transfer & Documentation | RM100,000 | 2% |
| 8. Programme Governance, IP, Legal & Administration | RM100,000 | 2% |
| 9. Technical / Programme Contingency | RM150,000 | 3% |
| TOTAL PROGRAMME | RM5,000,000 | 100% |

The cost architecture places 69% of total programme value into direct IP creation, AI product engineering and dedicated human capital. The remaining 31% provides the compute, tooling, data, integration, assurance, training, governance and risk capacity required to move the capability from concept through production readiness.

# 2. Costing Principles and Analytical Basis

The proposed budget is built around the following principles:

Asset creation: the programme must result in codified R.I.S.I.K methodology, reusable intellectual property, technical specifications and a deployable AI platform.

Delivery capacity: a dedicated multidisciplinary team is costed separately from IP and platform work so manpower is transparent and auditable.

Production orientation: funding includes data integration, deployment, security assurance, UAT, documentation and knowledge transfer rather than stopping at MVP completion.

AI-specific operating cost: GPU capacity, model consumption, vector/database services, observability and MLOps are recognised as first-class cost drivers.

Assurance and governance: cybersecurity, AI-output validation, auditability, data governance, programme controls and IP/legal matters are explicitly funded.

Controlled contingency: only 3% of the programme is reserved for technical and programme uncertainty, preserving cost discipline.

## 2.1 Key Costing Assumptions

| Assumption | Basis |
| --- | --- |
| Programme duration | 12 months from mobilisation to operational acceptance. |
| Core team | 7 dedicated roles, fully loaded at an average programme burn of RM150,000 per month. |
| Scope | Framework formalisation, AI platform engineering, integration, security assurance, pilot/UAT, production commissioning and knowledge transfer. |
| Infrastructure model | Combination of dedicated/private AI capacity and metered model/inference usage. |
| Data | Budget allows for commercial intelligence feeds, social/media/OSINT APIs and integration activity. |
| Contingency | 3% held centrally and released only against approved technical or programme risk. |

# 3. Consolidated RM5.0 Million Cost Structure

| Category | RM | % | Primary Cost Character |
| --- | --- | --- | --- |
| Framework & IP | RM750,000 | 15% | One-time build |
| AI Engineering | RM900,000 | 18% | One-time build |
| 7-Person Team | RM1,800,000 | 36% | Recurring / delivery |
| AI Infrastructure & Tooling | RM550,000 | 11% | Recurring / delivery |
| Data / Integration / Deployment | RM450,000 | 9% | Operationalisation / control |
| Cybersecurity & AI Assurance | RM200,000 | 4% | Operationalisation / control |
| Training & KT | RM100,000 | 2% | Operationalisation / control |
| Governance / IP / Legal | RM100,000 | 2% | Operationalisation / control |
| Contingency | RM150,000 | 3% | Operationalisation / control |

## 3.1 Cost Concentration Analysis

RM1.65 million (33%) is allocated to framework/IP and AI engineering - the direct creation of differentiated programme assets.

RM1.80 million (36%) is allocated to the seven-person core team - the largest single category and the principal execution capacity.

RM1.00 million (20%) is allocated to data, integration, deployment, assurance and programme support - the elements required to reach operational acceptance.

RM550,000 (11%) is allocated to AI infrastructure and engineering tooling - necessary to support inference, experimentation, MLOps, observability and secure development.

# 4. R.I.S.I.K Framework & IP Development - RM750,000

This workstream converts the R.I.S.I.K concept into a formal, codified and reusable methodology. It establishes the intellectual foundation that defines how Reality, Issue, Sentiment, Influence and Kontra Narrative are represented, scored, related and operationalised.

| Scope | Budget | Analytical Rationale |
| --- | --- | --- |
| R.I.S.I.K methodology formalisation | RM150,000 | Codifies operating model, definitions, decision logic and analyst workflow. |
| Reality intelligence methodology | RM90,000 | Defines evidence, source, context and reality-assessment structures. |
| Issue identification & prioritisation | RM90,000 | Establishes issue taxonomy, severity, priority and escalation logic. |
| Sentiment methodology | RM90,000 | Defines sentiment dimensions, confidence, temporal and audience interpretation. |
| Influence / actor-network methodology | RM100,000 | Defines actors, relationships, influence indicators and network-analysis logic. |
| Kontra Narrative methodology | RM100,000 | Defines response-generation doctrine, constraints, alignment and evaluation criteria. |
| Intelligence workflow, taxonomy & scoring | RM80,000 | Creates cross-module scoring, workflow, provenance and confidence structures. |
| IP documentation & framework specification | RM50,000 | Produces formal specifications, handover material and reusable IP artefacts. |
| TOTAL | RM750,000 | 15% of programme value. |

## 4.1 Expected Deliverables

R.I.S.I.K reference architecture and methodology specification.

Formal definitions, taxonomies, scoring models and confidence framework.

Analyst and system workflows across the five R.I.S.I.K dimensions.

IP package suitable for implementation, training, governance and future enhancement.

# 5. AI Engineering & Intelligence Capability Development - RM900,000

This workstream converts the codified framework into an operational AI-enabled intelligence platform. The cost is separated from team salaries because it represents defined engineering work-products and productisation value rather than payroll alone.

| Engineering Scope | Budget | Output |
| --- | --- | --- |
| LLM / AI reasoning architecture | RM160,000 | Reasoning patterns, model routing, prompt/system controls and AI decision services. |
| Agent orchestration & workflow engine | RM140,000 | Agent execution, task chaining, control flows and human-in-the-loop checkpoints. |
| RAG / knowledge architecture | RM120,000 | Retrieval, embeddings, knowledge context, grounding and source traceability. |
| Entity & relationship intelligence | RM100,000 | Entity extraction, resolution and relationship representation. |
| Sentiment & narrative analytics engine | RM100,000 | Machine-assisted sentiment, theme and narrative analysis. |
| Influence / network analytics | RM90,000 | Actor-network, propagation and influence analysis functions. |
| AI-assisted Kontra Narrative generation | RM90,000 | Controlled response and narrative recommendation capability. |
| Intelligence dashboard & visualisation | RM60,000 | Operational dashboards, analyst views and decision-support presentation. |
| API & interoperability framework | RM40,000 | Structured service interface for external integration. |
| TOTAL | RM900,000 | 18% of programme value. |

# 6. Dedicated Development Team - RM1,800,000

A seven-person core team provides continuous product, AI, platform, data, cybersecurity, UX and intelligence-analysis capacity throughout the 12-month programme. The fully loaded team allocation is RM150,000 per month.

| Role | Monthly Base | 12-Month Allocation | Primary Responsibility |
| --- | --- | --- | --- |
| Programme / Product Lead | RM22,000 | RM264,000 | Programme direction, product ownership, stakeholders and acceptance. |
| AI / ML Lead Engineer | RM22,000 | RM264,000 | Model architecture, AI engineering, evaluation and optimisation. |
| Platform / Backend Engineer | RM18,000 | RM216,000 | Core services, APIs, workflow and application backend. |
| Data / Knowledge Engineer | RM18,000 | RM216,000 | Data pipelines, RAG, vector/knowledge stores and data quality. |
| DevSecOps / Cybersecurity Engineer | RM20,000 | RM240,000 | Secure SDLC, CI/CD, deployment, hardening and observability. |
| Frontend / UX Engineer | RM15,000 | RM180,000 | Analyst interface, dashboard UX and visualisation. |
| Intelligence Analyst / QA Engineer | RM15,000 | RM180,000 | Use cases, QA, validation, analyst workflow and output testing. |
| Employment overhead / benefits / administration | - | RM240,000 | Statutory, benefits, HR, equipment/admin and delivery overhead. |
| TOTAL | RM130,000 base / month | RM1,800,000 | Fully loaded programme burn: RM150,000/month. |

## 6.1 Team Cost Interpretation

Direct salary-equivalent allocation totals RM1.56 million.

RM240,000 provides an approximately 15.4% load over direct manpower for employment overhead, staff support and administration.

Fully loaded annual cost averages approximately RM257,143 per team member, or approximately RM21,429 per person per month.

The team cost is distinct from tooling, infrastructure, external data, independent assurance and programme contingency.

# 7. AI Infrastructure, Tooling & Development Environment - RM550,000

| Component | Budget | Justification |
| --- | --- | --- |
| GPU / AI inference capacity | RM280,000 | Core model execution, experimentation, embeddings, batch processing and evaluation. |
| Model API / token consumption | RM80,000 | Flexible access to external or specialist models where required. |
| Development & AI engineering tools | RM50,000 | Developer productivity, model experimentation and technical utilities. |
| MLOps / CI-CD / DevSecOps | RM50,000 | Secure build, release, evaluation and deployment automation. |
| Monitoring, observability & logging | RM40,000 | Operational telemetry, auditability, performance and failure investigation. |
| Database, vector DB, storage & backup | RM50,000 | Persistent operational data, RAG stores and resilience. |
| TOTAL | RM550,000 | 11% of programme value. |

Cost-control principle AI infrastructure should be governed through quotas, environment separation, model-routing policy, usage dashboards and monthly consumption review. This prevents token/GPU expenditure from becoming an uncontrolled variable.

# 8. Data, Integration & Production Deployment - RM450,000

| Component | Budget | Purpose |
| --- | --- | --- |
| Intelligence feeds / data acquisition | RM150,000 | Licensed or commercial datasets required for reliable intelligence workflows. |
| Social / media / OSINT API integration | RM75,000 | Access and engineering for relevant external information sources. |
| Third-party / government system integration | RM75,000 | API, data exchange and interoperability with authorised systems. |
| Production deployment & environment setup | RM75,000 | Production environment, configuration, hardening and release support. |
| UAT, pilot & commissioning | RM75,000 | User validation, defect resolution, acceptance and operational commissioning. |
| TOTAL | RM450,000 | 9% of programme value. |

# 9. Cybersecurity, AI Assurance & Validation - RM200,000

This allocation protects the operational credibility of a government or strategic-intelligence grade platform. It covers independent and internal validation activities that should not be absorbed invisibly into engineering manpower.

Secure architecture and threat-model review.

Application, API and infrastructure penetration testing.

Model/prompt-security and abuse-case assessment.

AI hallucination, grounding, confidence and output-quality evaluation.

Identity, access control, logging and auditability validation.

Data governance, provenance and handling controls.

Remediation verification before final operational acceptance.

Budget envelope: RM200,000 (4% of programme value).

# 10. Training, Knowledge Transfer & Documentation - RM100,000

Administrator and platform-operator training.

Intelligence analyst workflow and R.I.S.I.K methodology training.

Technical handover for deployment, troubleshooting and maintenance.

System architecture, API, security and operational documentation.

SOPs, runbooks, user guides and train-the-trainer materials.

The objective is to avoid a technically complete platform that remains dependent on the original build team for routine operation.

# 11. Programme Governance, IP, Legal & Administration - RM100,000

Programme steering, reporting, risk/issue management and change control.

Stakeholder coordination and formal acceptance administration.

IP ownership, licensing, third-party software and data-use governance.

Legal/contractual support for data, integration and external services.

Financial tracking, procurement coordination and documentation control.

# 12. Technical / Programme Contingency - RM150,000

The contingency is limited to 3% of the total programme value and should be centrally controlled rather than distributed to workstreams. It is intended for approved changes arising from technical uncertainty, external dependency changes, data-source changes, model/infrastructure cost variation or integration complexity.

Release rule Contingency should only be drawn against a documented risk/change item, impact assessment, approval authority and updated forecast. Unused contingency should remain uncommitted.

# 13. 12-Month Cost Phasing

The following phasing is an analytical planning model rather than a contractual billing schedule. It front-loads framework design and architecture, sustains team and tooling costs throughout the year, and shifts more deployment, assurance and training cost into the later phases.

| Cost Category | Q1 | Q2 | Q3 | Q4 | Total |
| --- | --- | --- | --- | --- | --- |
| Framework & IP | RM300,000 | RM250,000 | RM150,000 | RM50,000 | RM750,000 |
| AI Engineering | RM150,000 | RM300,000 | RM300,000 | RM150,000 | RM900,000 |
| 7-Person Team | RM450,000 | RM450,000 | RM450,000 | RM450,000 | RM1,800,000 |
| Infrastructure & Tooling | RM160,000 | RM140,000 | RM130,000 | RM120,000 | RM550,000 |
| Data / Integration / Deployment | RM60,000 | RM100,000 | RM140,000 | RM150,000 | RM450,000 |
| Cybersecurity & AI Assurance | RM20,000 | RM30,000 | RM60,000 | RM90,000 | RM200,000 |
| Training & Knowledge Transfer | RM0 | RM10,000 | RM30,000 | RM60,000 | RM100,000 |
| Governance / IP / Legal | RM25,000 | RM25,000 | RM25,000 | RM25,000 | RM100,000 |
| Contingency | RM0 | RM0 | RM25,000 | RM125,000 | RM150,000 |
| TOTAL | RM1,165,000 | RM1,305,000 | RM1,310,000 | RM1,220,000 | RM5,000,000 |

## 13.1 Indicative Programme Phase Mapping

| Period | Primary Focus | Indicative Spend |
| --- | --- | --- |
| Months 1-3 | Mobilisation, framework formalisation, architecture, baseline environments and initial AI engineering. | RM1,165,000 |
| Months 4-6 | Core AI capability build, knowledge/RAG services, workflows, interfaces and early integrations. | RM1,305,000 |
| Months 7-9 | Integrated productisation, data feeds, pilot preparation, assurance and performance optimisation. | RM1,310,000 |
| Months 10-12 | Production deployment, UAT, assurance closure, documentation, training, commissioning and contingency closure. | RM1,220,000 |

# 14. Cost-to-Deliverable Traceability

| Programme Asset / Outcome | Primary Cost Pools | Indicative Value Supported |
| --- | --- | --- |
| Codified R.I.S.I.K intellectual property | Framework & IP; team; governance | Formal methodology, taxonomies, scoring, workflows and reusable specification. |
| AI-enabled intelligence platform | AI engineering; team; tooling | Operational AI reasoning, RAG, agents, analytics, APIs, dashboards and intelligence workflows. |
| Production-grade operating environment | Tooling; data/integration/deployment; team | Secure environments, data flows, deployment automation, observability and production readiness. |
| Trusted / assured capability | Cybersecurity & AI assurance; team | Security testing, AI validation, auditability, remediation and acceptance evidence. |
| Sustainable operational capability | Training & KT; documentation; governance | Trained operators/analysts, runbooks, SOPs, handover and governance controls. |

# 15. Cost Governance, Controls and Acceptance

A RM5.0 million programme should be governed by deliverable-based financial controls. Recommended controls are:

Establish one approved programme baseline covering scope, budget, schedule and acceptance criteria.

Track actual and committed spend monthly by the nine cost categories in this document.

Require purchase-order or approval references for external tooling, compute, data and assurance expenditure.

Separate baseline budget, approved changes and contingency drawdown in financial reporting.

Tie major payment or internal cost-release gates to technical deliverables and formal acceptance evidence.

Review AI compute/token utilisation monthly and forecast remaining consumption against planned workloads.

Maintain an IP register identifying methodology artefacts, source code, models/configuration, data rights and third-party dependencies.

Apply change control to new integrations, data sources, major model changes or scope expansion that materially affects cost.

## 15.1 Recommended Stage Gates

| Gate | Target Timing | Acceptance Focus |
| --- | --- | --- |
| G1 - Mobilisation & Design Baseline | End Month 2 | Programme plan, R.I.S.I.K framework baseline, architecture, security and environment plan. |
| G2 - Core Capability Demonstration | End Month 5 | Working AI reasoning/RAG/agent capabilities and core R.I.S.I.K module workflows. |
| G3 - Integrated Pilot Readiness | End Month 8 | Integrated platform, representative data feeds, dashboards, initial assurance and pilot scenarios. |
| G4 - Production Readiness | End Month 10 | Deployment readiness, remediation, operational documentation and UAT entry. |
| G5 - Operational Acceptance | End Month 12 | UAT closure, security/AI assurance, training, handover, final documentation and commissioning. |

# 16. Conclusion and Funding Position

The proposed RM5.0 million cost structure is balanced around the creation of durable intellectual property, dedicated engineering capacity and the operational controls required for a credible AI-enabled strategic intelligence platform. It avoids the common weakness of treating the initiative as a software build while excluding the costs of data, AI infrastructure, security assurance, integration, knowledge transfer and production commissioning.

Recommended programme description RM5.0 million investment for the development, productisation, deployment and operationalisation of the R.I.S.I.K AI-enabled strategic intelligence capability over a 12-month programme.

## 16.1 Value Created by the Programme

R.I.S.I.K Intellectual Property - codified methodology, taxonomy, scoring and operating doctrine.

R.I.S.I.K AI Platform - reasoning, analytics, knowledge, agentic workflows and command interface.

Operational Capability - integrated data, deployment environment, trained users, security assurance and operating procedures.

Reusable Strategic Capability - an architecture and knowledge base that can be extended to future authorised strategic-intelligence, policy, communications and government use cases.

On this basis, the RM5.0 million should be evaluated against the complete capability and asset base created over 12 months, rather than against developer headcount or coding effort alone.

End of document