ARAS INTEGRASI

# Government Digitalisation & AI Cohort Program

Program Management Framework for Official Alignment with Encik Razale

PROGRAM INTENT Establish a repeatable government technology production mechanism that converts real agency problems into validated pilots, reusable digital assets, governed intellectual property, cross-agency adoption and scalable commercialisation.

| Document Control | Detail |
| --- | --- |
| Document Status | Draft for Official Alignment |
| Primary Alignment Stakeholder | Encik Razale Bin Ibrahim |
| Program Sponsor / Lead | DAF |
| Program Type | Joint Digitalisation & AI Capability Development Initiative |
| Initial Proof-Point Workstreams | DOSM KDRM |
| Planning Horizon | 3 / 6 / 9-month cohort lifecycle |
| Date | 26 August 2026 |

CONFIDENTIAL WORKING DOCUMENT • FOR PROGRAM ALIGNMENT

# 1. Executive Program Alignment

The Cohort Program is proposed as a structured joint mechanism between Aras Integrasi and participating government agencies to accelerate the adoption of digitalisation and artificial intelligence through focused, execution-oriented sub-cohorts.

The program is designed to move beyond awareness, training or isolated proof-of-concept activity. Its purpose is to establish a repeatable operating model that links agency problems, technical development, documentation, intellectual property governance, validation, reuse, adoption and eventual commercialisation.

NORTH STAR Government Problem → Cohort → Pilot → Validation → URS/SRS → Productisation → IP & Governance → Technology Catalogue → Cross-Agency Adoption

## 1.1 Aligned Outcomes

1. Agreement in principle on the Cohort Program mandate and its positioning as an official execution mechanism.

2. Alignment on the focused sub-cohort model, with an identified agency champion and clearly defined use case for each cohort.

3. Alignment on the 3 / 6 / 9-month delivery lifecycle and associated decision gates.

4. Agreement to formalise the Intellectual Property Framework and proceed with a dedicated one-day IP working session.

5. Confirmation of Hermes, MyMesyuarat and DOSM as the initial workstreams used to prove and refine the operating model.

## 1.2 Program Success Definition

The program is successful when it consistently produces:

validated solutions to real government operational problems;

documented and reusable digital assets rather than one-off prototypes;

clear ownership and governance of jointly developed intellectual property;

credible agency champions who can demonstrate value and accelerate adoption;

a trusted catalogue of reusable technology assets for wider government use; and

a sustainable pathway from government adoption to commercial and regional scale.

# 2. Program Charter

| Charter Element | Definition |
| --- | --- |
| Purpose | Accelerate government digitalisation and AI adoption by converting priority agency problems into validated, reusable and governable technology outcomes. |
| Strategic Approach | Focused sub-cohorts, rapid pilots, formal documentation, controlled validation, IP governance and progressive scale. |
| Primary Stakeholders | Encik Razale, Ahmad Faurani, participating government agency champions, Aras delivery teams, programme managers and supporting ecosystem partners. |
| Initial Scope | Initial proof-point workstream. |
| Delivery Model | 3 / 6 / 9-month lifecycle with formal review gates and measurable outputs at each phase. |
| Scaling Model | Build once, validate, document, catalogue and enable reuse across additional agencies. |
| Sustainability Model | Adoption first, demonstrate value, measure usage, build trust and introduce fit-for-purpose commercial models as solutions mature. |

## 2.1 Program Principles

Execution over participation — Cohorts are intentionally small and focused. Participation must translate into an owned use case and active implementation.

Agency ownership — Every cohort requires a government-side champion with responsibility for problem definition, validation and internal mobilisation.

Evidence before scale — Solutions advance only after demonstrated operational value and completion of defined validation criteria.

Document for reuse — Technical and operational knowledge must be captured through URS, SRS, reference architecture and supporting documentation.

Govern IP deliberately — Ownership, licensing, reuse and commercialisation rights are defined before solutions are scaled.

Standardise for government reuse — Validated solutions should be capable of being catalogued and adopted by other agencies without rebuilding from zero.

# 3. Cohort Operating Model

The Cohort Program should operate as a managed production system for government technology capability, not as a large general-interest engagement forum.

## 3.1 Standard Cohort Unit

| Component | Minimum Requirement |
| --- | --- |
| Agency | A participating government organisation that owns the operational problem or opportunity. |
| Agency Champion | A motivated officer with sufficient ownership to coordinate users, validate requirements and sustain internal momentum. |
| Use Case | A specific operational problem with a measurable target outcome. |
| Aras Delivery Team | Technical, product and programme resources assigned to convert the use case into a working pilot. |
| Pilot / Prototype | A testable implementation that demonstrates practical value within the target workflow. |
| Documentation | URS, SRS, technical notes, deployment requirements and user/operating guidance as appropriate. |
| IP Treatment | Defined background IP, foreground IP, usage rights, ownership, reuse and commercial rights. |
| Decision Gate | Formal continue / refine / hold / stop decision based on evidence. |
| Scale Path | Defined pathway for production deployment, cross-agency reuse, catalogue inclusion and commercialisation. |

## 3.2 Agency Champion / KOL Role

The program should intentionally cultivate credible public-sector champions who can demonstrate tangible outcomes, influence adoption and reduce organisational resistance to AI and digitalisation.

Own the agency problem statement and intended outcome.

Mobilise relevant users and working-level stakeholders.

Facilitate validation of the pilot within the actual operating environment.

Provide structured feedback and support decision-gate reviews.

Act as a credible internal advocate when the solution demonstrates value.

# 4. 3 / 6 / 9-Month Delivery Lifecycle

| Phase | Primary Objective | Core Activities | Gate Output |
| --- | --- | --- | --- |
| 0–3 Months Discover & Pilot | Prove relevance and practical value. | Use-case selection; champion confirmation; requirements discovery; prototype/pilot; user feedback; initial value validation. | Gate 1: Continue, refine or stop. |
| 3–6 Months Stabilise & Productise | Convert the pilot into a repeatable, documented solution. | Architecture refinement; URS/SRS; security and technical validation; bug fixing; product hardening; documentation; IP classification. | Gate 2: Productisation readiness. |
| 6–9 Months Scale & Institutionalise | Prepare for wider government adoption and sustainable operation. | Production readiness; deployment model; catalogue inclusion; reuse by other agencies; showcase; support model; commercialisation assessment. | Gate 3: Scale / reuse / commercialise. |

## 4.1 Decision-Gate Discipline

Each workstream should be reviewed against explicit evidence before progressing. A workstream should not advance simply because development activity has occurred.

| Gate | Decision Question | Minimum Evidence |
| --- | --- | --- |
| Gate 1 | Does the pilot solve a real and important agency problem? | Champion validation, user feedback, working pilot and measurable value hypothesis. |
| Gate 2 | Is the solution sufficiently stable, documented and governable to become a reusable product asset? | URS/SRS, architecture, validation record, product backlog, IP classification and operating requirements. |
| Gate 3 | Is the solution ready for wider deployment or catalogue inclusion? | Production readiness, support model, deployment package, ownership/governance, adoption evidence and scale case. |

# 5. Initial Workstream Portfolio

The first three workstreams should be treated as proof points for the Cohort Program methodology. Their purpose is both to deliver useful outcomes and to test the repeatability of the governance, documentation and scale model.

| Workstream | Strategic Role | Initial Focus | Expected Cohort Output |
| --- | --- | --- | --- |

## 5.1 Workstream Charter — Minimum Required Fields

Problem statement and target user group.

Named agency champion and Aras workstream owner.

Target outcome and measurable success criteria.

Dependencies, assumptions and constraints.

Pilot scope and exclusions.

3 / 6 / 9-month milestones.

Required documentation and validation evidence.

IP treatment and intended reuse pathway.

Decision-gate criteria and accountable approver.

# 6. Program Governance & Management

GOVERNANCE INTENT Maintain strategic alignment at sponsor level while giving each workstream clear operational ownership, measurable deliverables and time-bound decisions.

## 6.1 Proposed Governance Structure

| Role | Primary Accountability |
| --- | --- |
| Strategic Alignment Stakeholder — Encik Razale | Align the programme mandate, operating model and strategic direction; provide guidance on institutionalisation and programme progression. |
| Program Sponsor / Lead — Ahmad Faurani | Own overall programme design, stakeholder alignment, resourcing, escalation and programme-level outcomes. |
| IP Review — Encik Razale & Naim | Review the IP Framework and resolve key principles for ownership, usage, reuse, licensing and commercialisation. |
| Programme Managers | Coordinate cohort execution, schedules, reviews, dependencies, risk tracking, evidence collection and quarterly reporting. |
| Agency Champion | Own the use case, mobilise agency users, validate requirements and champion adoption. |
| Workstream Technical / Product Team | Design, build, document, validate and prepare the solution for productisation and scale. |
| Commercial / Ecosystem Team | Develop adoption, partnership, sustainability and future regional commercialisation pathways. |

## 6.2 Management Rhythm

| Cadence | Forum | Purpose |
| --- | --- | --- |
| Weekly | Workstream Delivery Review | Progress, blockers, dependencies, next deliverables and evidence required for the next gate. |
| Monthly | Program Management Review | Portfolio status, cross-workstream issues, resource allocation, risk and escalation. |
| Quarterly | Strategic Cohort Review | Outcome review, programme adjustments, new cohort intake, scaling decisions and stakeholder alignment. |
| At Decision Gates | Gate Review | Formal continue / refine / hold / stop decision based on documented evidence. |

# 7. IP, Reuse & Government Technology Catalogue

## 7.1 Intellectual Property Framework

The Intellectual Property Framework should be treated as a foundational programme control because the cohort model is intended to create reusable and potentially commercialisable technology assets.

Background / pre-existing IP.

Foreground IP created during cohort activity.

Jointly developed IP.

Government usage and deployment rights.

Cross-agency reuse rights.

Licensing and support rights.

Derivative works and future development.

Commercialisation and regional market rights.

PROPOSED NEXT STEP Share the initial IP Framework with for preliminary review, then conduct a focused one-day working session to resolve the principles required before wider programme scale.

## 7.2 Government Technology Catalogue / Marketplace

Validated cohort outputs should progressively feed a trusted catalogue of government-ready technology assets. The catalogue is intended to enable controlled discovery, reuse and deployment—not merely source-code storage.

| Catalogue Asset | Required Metadata / Control |
| --- | --- |
| AI Models | Version, owner, validation status, intended use, deployment requirements and assurance record. |
| Applications / Components | Owner, release status, dependencies, technical documentation and support model. |
| APIs / Integration Patterns | Interface specification, security requirements, dependencies and reference implementation. |
| URS / BRS / SRS | Approved version, originating use case, owner and applicability to future deployments. |
| Reference Architectures | Deployment pattern, infrastructure assumptions, security model and integration dependencies. |
| Reusable Automation | Purpose, operating conditions, version history and validation status. |

# 8. Adoption, Sustainability & Scale

STRATEGIC SEQUENCE Adoption First → Demonstrate Value → Build Trust → Measure Usage → Standardise → Scale → Monetise

## 8.1 Sustainability Pathway

Commercialisation should follow demonstrated government value. Early cohort activity should prioritise credibility, adoption evidence and reusable capability while progressively defining fit-for-purpose commercial models for mature solutions.

usage-based or token-based services;

managed service arrangements;

product or platform licensing;

implementation and integration services;

support and lifecycle services; and

regional commercialisation through suitable ecosystem or incubation partners.

## 8.2 Program-Level KPIs

| KPI Area | Illustrative Measure |
| --- | --- |
| Cohort Activation | Number of active sub-cohorts with named agency champions and approved use cases. |
| Pilot Conversion | Percentage of initiated cohorts reaching a validated pilot. |
| Productisation | Percentage of validated pilots completing required documentation and Gate 2. |
| Reuse | Number of technology assets adopted or evaluated by more than one agency. |
| Time-to-Value | Elapsed time from use-case approval to working pilot. |
| Champion Development | Number of credible public-sector champions actively supporting adoption. |
| Catalogue Growth | Number of validated, documented reusable assets admitted to the catalogue. |
| Scale / Sustainability | Number of solutions progressing to wider deployment, support model or commercial pathway. |

# 9. Immediate Program Activation Plan

| Priority | Owner | Action | Required Output |
| --- | --- | --- | --- |
| P0 |  | Prepare and circulate the Cohort Program Framework for official alignment. | Aligned programme mandate and operating model. |
| P0 |  | Share the IP Framework | Initial comments and issues requiring resolution. |
| P0 |  | Review the IP Framework. | Guidance on ownership, usage, reuse and commercialisation principles. |
| P0 |  | Define the initial workstream charters. | Named owners, scope, milestones, success criteria and decision gates. |
| P1 |  | Formalise the 3 / 6 / 9-month lifecycle as the standard delivery methodology. | Standard cohort playbook and gate checklist. |
| P1 |  | Identify initial agency champions and required participants. | Confirmed cohort participant / champion registry. |
| P1 |  | Define the minimum viable Government Technology Catalogue. | Catalogue architecture, metadata model and governance requirements. |
| P1 |  | Schedule the dedicated IP working session. | One-day workshop with agreed decision agenda. |
| P1 |  | Define programme-management capacity and assignment model. | PM allocation plan aligned to active cohort volume. |
| P2 |  | Develop regionalisation and ecosystem pathways for mature solutions. | Partner map and commercialisation options. |

# 10. Alignment Decision Record

This section is intended to capture the outcome of the formal alignment discussion with Encik Razale and convert the discussion directly into an executable programme mandate.

| Decision Item | Proposed Position | Alignment Status / Notes |
| --- | --- | --- |
| Program Mandate | Proceed with the Cohort Program as a structured government digitalisation and AI execution mechanism. | ____________________________ |
| Operating Model | Use focused sub-cohorts with named agency champions and defined use cases. | ____________________________ |
| Lifecycle | Adopt the 3 / 6 / 9-month lifecycle with formal decision gates. | ____________________________ |
| Initial Workstreams | Use Hermes, MyMesyuarat and DOSM as initial proof points. | ____________________________ |
| IP Governance | Proceed with initial review followed by a dedicated one-day IP working session. | ____________________________ |
| Technology Catalogue | Develop a trusted catalogue for validated reusable government technology assets. | ____________________________ |
| Governance | Activate weekly, monthly and quarterly programme-management rhythms. | ____________________________ |

TARGET ALIGNMENT OUTCOME Agreement in principle on the Cohort Program → approval to formalise the framework → confirmation of initial workstreams → activation of IP review → commencement of the first cohort execution cycle.

## 10.1 Immediate Next Step After Alignment

Upon alignment, the programme should immediately transition from framework design into controlled activation: issue the workstream charters, confirm agency champions, establish the programme review cadence, initiate the IP review and begin the first 0–3 month Discover & Pilot cycle.

# 11. Formal Alignment Sign-Off

Sign-off below records completion of the initial programme alignment review and authorises progression into the agreed activation actions.

| Prepared by | Alignment / Review |
| --- | --- |
| Ahmad Faurani Program Sponsor / Lead Date: __________________ | Encik Razale Strategic Alignment Stakeholder Date: __________________ |