CYBERDSA 2026

# Executive Stakeholder Engagement
& Activation Framework

Document 1 — Operational Playbook for CyberSecurity Malaysia and NACSA Stakeholder Activation

Strategic Intent

Secure the stakeholder alignment required to position the Aras Integrasi × CyberSecurity Malaysia collaboration at CyberDSA 2026 as a credible, commercially actionable and nationally aligned sovereign cybersecurity capability.

Status: Internal Activation Framework | Version 1.1 | 23 August 2026

# 1. Executive Summary

CyberDSA 2026 is being used as an activation point for a broader strategic outcome: establishing Aras Integrasi and CyberSecurity Malaysia (CSM) as an aligned ecosystem capable of presenting, commercialising and operationalising national-grade sovereign cybersecurity technology.

The immediate priority is not additional product development. The priority is stakeholder alignment through a controlled dependency chain. The programme must secure CSM partnership sponsorship, commercial ownership, operational enablement, technical validation and only then market/media amplification before seeking higher-level national strategic alignment with NACSA.

Primary Mission Create a sequence of willing, informed and accountable stakeholders who each own a defined part of the CyberDSA outcome — partnership sponsorship, commercial activation, operational coordination, technical confidence, market/media amplification and national strategic alignment.

## 1.1 Required End State

CSM and Aras Integrasi share one coherent CyberDSA positioning and understand the intended national-grade sovereign technology story.

Each critical stakeholder has one explicit role, one primary ask and one measurable outcome.

Commercial follow-through is designed before the event rather than improvised after the event.

Operational coordination, access paths and implementation touchpoints are established before formal technical validation.

CSM technical leadership validates architecture, deployment posture and governance against defined operating conditions; Aras remains responsible for POC execution.

Marketing/media activation follows technical clearance; NACSA engagement follows only after all CSM stakeholder gates are materially aligned.

## 1.2 Immediate Priority

| ACTION | Secure Azrul Nazim’s buy-in and sponsorship for the governing sequence: Zulfeka bin Zainal Abidin → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan → Dr. Megat. |
| --- | --- |
| OWNER | DAF / Aras Integrasi |
| TIMING | Priority 1 — initiate first |

# 2. Mission, Scope and Activation Logic

Mission Objective. Engineer the stakeholder conditions required for CyberDSA 2026 to become a credible launch and market-activation platform for an integrated Malaysian sovereign cybersecurity capability, with Aras Integrasi acting as the operational technology integrator and CSM acting as a strategic ecosystem partner.

## 2.1 What This Framework Covers

Stakeholder roles and influence objectives.

Engagement sequence and dependencies.

The specific decision or commitment required from each stakeholder.

Meeting design, messaging and follow-up mechanics.

Activation governance, cadence and escalation.

Success measures and executive tracking.

## 2.2 What This Framework Does Not Cover

Detailed product architecture, development backlog or engineering delivery plan.

A standalone CyberDSA media plan or creative campaign plan.

A full post-event sales operating model.

A request for CSM technical personnel to execute Aras POCs; Aras will support and deliver the POC activity on CSM’s behalf where required.

## 2.3 Activation Doctrine

1. Align before asking — Stakeholders should first understand the intended outcome and why their role matters before receiving a task or commitment request.

2. One stakeholder, one primary ask — Avoid broad or ambiguous requests. Each engagement should close on one principal commitment.

3. Preserve the dependency chain before external validation — CSM activation proceeds Azrul Nazim → Zulfeka bin Zainal Abidin  → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan. Dr. Megat / NACSA is approached only after those CSM gates are materially aligned.

4. Make participation valuable — Each stakeholder should see a direct institutional benefit — partnership relevance, commercial opportunity, visibility, technical credibility or national contribution.

5. Convert verbal support into operating behaviour — Every positive discussion must produce a named next action, owner and follow-up date.

6. Keep the narrative integrated — The three product pillars are proof of an integrated sovereign capability, not disconnected product launches.

# 3. Stakeholder Architecture

The stakeholder model is deliberately compact. The objective is to create a clear chain of alignment rather than a large stakeholder committee with diluted accountability.

| # | Stakeholder | Role Lens | Primary Objective | Required Outcome |
| --- | --- | --- | --- | --- |
| 1 | Azrul Nazim | Partnership & Alliance | Anchor the CSM–Aras strategic partnership and secure internal sponsorship for the joint CyberDSA narrative and activation sequence. | Partnership buy-in and sponsorship |
| 2 | Zulfeka bin Zainal Abidin | Commercial | Translate the partnership narrative into commercial objectives, priority accounts and post-event conversion ownership. | Commercial ownership |
| 3 | Ts. Mohammad Zaharudin Bin Ahmad Darus | Operational / Technical Coordination | Translate commercial intent into practical access, coordination, implementation touchpoints and issue-resolution mechanisms that frame technical validation. | Operational pathway defined |
| 4 | Wan Roshaimi Wan Abdullah | CTO / Technology Strategy | Validate the technical posture, architecture fit, integration boundaries and governance position against the agreed operational conditions. | Technical confidence and strategic fit |
| 5 | Balamurugan Nallapan | Marketing & Media Engagement | Convert the validated partnership, commercial, operational and technical position into a coherent external story across branding, media and stakeholder communications. | Controlled market visibility and message consistency |
| 6 | Dr. Megat | NACSA – National Strategic Alignment | Assess alignment of the mature proposition with national sovereign cybersecurity priorities and provide an appropriate pathway for strategic recognition/engagement. | National strategic alignment |

## 3.1 Governing Activation Sequence

Azrul Nazim → Zulfeka bin Zainal Abidin  → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan → Dr. Megat

This is the governing social-engineered activation flow for the programme. It deliberately builds the proposition from partnership legitimacy to commercial purpose, then to executable operating conditions, technical defensibility, controlled market amplification and finally national strategic alignment. Preparation may overlap, but stakeholder closure should not bypass the dependency order.

# 4. Engagement Sequence and Decision Gates

| Decision Gate | Lead Stakeholder | Close Required | Control Point |
| --- | --- | --- | --- |
| Gate 1 — Partnership Alignment | Azrul Nazim | Confirm the partnership intent, joint CyberDSA narrative and CSM sponsorship pathway. | Do not activate broader CSM asks until the partnership narrative and stakeholder sequence are sufficiently stable. |
| Gate 2 — Commercial Ownership | Zulfeka bin Zainal Abidin | Agree what commercial success looks like, target engagement priorities and post-event follow-through. | Commercial intent must be clear before operational coordination is designed. |
| Gate 3 — Operational Enablement | Ts. Mohammad Zaharudin Bin Ahmad Darus | Agree implementation touchpoints, access, contact chain, dependencies and issue-resolution mechanisms required to support the intended commercial and POC activity. | Define the operating conditions before escalating the proposition for CTO-level technical validation. |
| Gate 4 — Technical Confidence | Wan Roshaimi Wan Abdullah | Validate technical posture, architecture fit, integration boundaries, governance concerns and defensible public claims. | Technical leadership validates; Aras remains responsible for POC execution. No external amplification should outrun the cleared technical position. |
| Gate 5 — Market & Media Activation | Balamurugan Nallapan | Translate the validated proposition into external messaging, spokesperson coordination, media opportunities and amplification responsibilities. | Public messaging follows the approved partnership, commercial, operational and technical position; avoid premature claims or fragmented product messaging. |
| Gate 6 — National Strategic Alignment | Dr. Megat | Present a mature proposition and explore NACSA alignment, acknowledgement, participation or an appropriate strategic pathway. | Approach with evidence of completed CSM alignment, not as an unformed endorsement request. |

# 5. Stakeholder Engagement Playbooks

Each playbook below is designed to produce one defined commitment. Secondary discussion points are permitted, but the primary ask should remain clear throughout the engagement.

## 5.1 Azrul Nazim — Partnership & Alliance Anchor

| Role Lens | Partnership & Alliance |
| --- | --- |
| Engagement Purpose | Position the CyberDSA initiative as a strategic CSM–Aras alliance outcome rather than a vendor-led product promotion. |
| Primary Ask | Secure Azrul Nazim’s explicit support for the joint CyberDSA narrative and his sponsorship for the relevant CSM stakeholders to participate in the activation sequence. |
| Stakeholder Value | Strengthens CSM’s partnership visibility, demonstrates tangible post-MOU execution, and creates a coherent institutional story around sovereign technology development and market activation. |

### Message Emphasis

CyberDSA should demonstrate what the CSM–Aras partnership can operationalise, not merely what individual products can do.

The collaboration can be framed as Partnership → Sovereign Technology Development → National Market Activation.

Aras will carry the execution burden; CSM’s value is strategic partnership, institutional credibility and ecosystem activation.

The immediate ask is alignment and sponsorship, not operational workload.

Required Close: Agreement on narrative direction, the governing activation sequence and permission/support to mobilise the commercial, operational, technical and marketing/media tracks in order.

Follow-through: Send a short written alignment note within 24 hours, listing the agreed narrative and the next stakeholder sequence: Zulfeka bin Zainal Abidin  → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan.

## 5.2 Zulfeka bin Zainal Abidin  — Commercial Activation Owner

| Role Lens | Head of Commercial |
| --- | --- |
| Engagement Purpose | Convert the CyberDSA narrative into measurable market activity and establish a post-event commercial conversion pathway. |
| Primary Ask | Agree the priority market segments/accounts, the commercial engagement mechanism at CyberDSA and the post-event follow-up model jointly supported by CSM and Aras. |
| Stakeholder Value | Creates commercial proof that the partnership can generate market outcomes, not only event visibility. |

### Message Emphasis

The event must produce a managed pipeline, not a list of visitors.

Aras can lead demos, solutioning and POC execution; the commercial track should focus on access, prioritisation and conversion.

The strongest accounts are those where CSM credibility and Aras delivery capability create a differentiated entry point.

Post-event ownership must be agreed before the event.

Required Close: Named priority accounts/segments, clear CSM and Aras commercial owners, agreed lead-capture and follow-up mechanism, and target outcomes for meetings/POCs.

Follow-through: Create a one-page joint target-account and follow-up sheet; pass the agreed commercial priorities and use-case context into Ts. Mohammad Zaharudin Bin Ahmad Darus’s operational-enablement gate.

## 5.3 Ts. Mohammad Zaharudin Bin Ahmad Darus — Operational Coordination & Enablement

| Role Lens | Operational / Technical Coordination |
| --- | --- |
| Engagement Purpose | Translate the agreed partnership and commercial intent into practical CSM–Aras operating conditions so technical validation occurs against real access, coordination and implementation boundaries. |
| Primary Ask | Agree the operational touchpoints, access requirements, contact chain, implementation dependencies and issue-resolution path necessary to support CyberDSA readiness and Aras-led POC activity. |
| Stakeholder Value | Reduces execution friction, clarifies institutional interfaces and gives CSM technical leadership a concrete operating context for architecture and governance validation. |

### Message Emphasis

The aim is to make execution easy for both organisations and to convert commercial intent into an executable operating pathway.

Aras owns POC delivery; CSM enables relevant access, coordination and institutional interfaces.

Operational dependencies and implementation touchpoints should be explicit before the proposition is taken to the CTO for formal technical validation.

Issues should have a named owner and fast resolution path rather than being allowed to circulate across multiple teams.

Required Close: Named operational contacts, agreed coordination channel, access requirements, implementation dependencies, issue escalation path and a clear input set for Wan Roshaimi Wan Abdullah’s technical-validation gate.

Follow-through: Maintain a short operational-readiness note and action register; hand the agreed interfaces, dependencies and constraints into Wan Roshaimi Wan Abdullah’s technical alignment session.

## 5.4 Wan Roshaimi Wan Abdullah — Technology Strategy & Governance

| Role Lens | CTO / Technology Strategy |
| --- | --- |
| Engagement Purpose | Establish technical credibility and strategic architecture alignment after the relevant commercial objectives and operating conditions have been defined, without transferring Aras delivery obligations to the CSM technical team. |
| Primary Ask | Validate the technical narrative, integration posture, architecture principles, operational boundaries and key governance considerations that should be represented at CyberDSA. |
| Stakeholder Value | Gives CSM confidence that the proposition is technically defensible and appropriately aligned with its technology environment and institutional responsibilities. |

### Message Emphasis

Aras will support and execute the POC activity; CSM technical leadership is not being asked to provide POC delivery resources.

The CTO engagement is about architecture, governance, integration boundaries and long-term fit, using the operating conditions established with Ts. Mohammad Zaharudin Bin Ahmad Darus as concrete context.

Technical claims intended for public use must be accurate, defensible and consistent with the validated deployment model; the cleared position becomes the input to Balamurugan Nallapan’s activation.

Any integration dependencies should be surfaced early so they can be managed before the event.

Required Close: Technical narrative validation, explicit integration considerations, identified red lines/constraints and agreement on any technical representation required at CyberDSA.

Follow-through: Capture decisions in a technical alignment note, route execution actions back to Aras owners, and provide Balamurugan Nallapan with the technically cleared claims, constraints and proof points for external activation.

## 5.5 Balamurugan Nallapan — Marketing & Media Engagement Owner

| Role Lens | Marketing & Media Engagement |
| --- | --- |
| Engagement Purpose | Externalise the now-aligned proposition through one consistent public narrative after partnership, commercial, operational and technical positions have been established. |
| Primary Ask | Agree a joint marketing/media activation plan based on the technically validated national-grade, full-stack sovereign technology narrative. |
| Stakeholder Value | Positions CSM as an active national ecosystem partner while protecting message accuracy, preventing fragmented claims and directing attention toward measurable market engagement. |

### Message Emphasis

The media story is the emergence of an integrated Malaysian sovereign cybersecurity capability, not three disconnected products.

Public claims must trace back to the technical position validated with Wan Roshaimi Wan Abdullah; marketing should amplify proof, not create new technical claims.

CSM’s role should be visible as an ecosystem and institutional partner while Aras is positioned as the integration and operationalisation engine.

Media activity should lead audiences toward qualified meetings, demos and post-event engagement rather than visibility alone.

Required Close: Agreed message house, spokesperson roles, media/branding touchpoints, content approval path and activation calendar based on the validated technical and commercial position.

Follow-through: Run a compact editorial and media readiness checkpoint each week; route any material change in technical claims or architecture positioning back through Wan Roshaimi Wan Abdullah / DAF before publication.

## 5.6 Dr. Megat — NACSA Strategic Alignment for Sovereign Product

| Role Lens | National Strategic Alignment |
| --- | --- |
| Engagement Purpose | Position the integrated proposition within the broader national cybersecurity context once CSM alignment is mature and internally coherent. |
| Primary Ask | Seek strategic alignment on the sovereign capability direction and identify the appropriate form of NACSA engagement — acknowledgement, participation, policy alignment, evaluation pathway or other suitable mechanism. |
| Stakeholder Value | Provides a pathway for the initiative to be understood in the context of national priorities without overreaching into a premature or transactional endorsement request. |

### Message Emphasis

The proposition should be presented as a Malaysian capability that has already progressed through partnership sponsorship, commercial ownership, operational enablement, technical validation and market/media alignment.

The request is for strategic alignment and the appropriate national pathway, not a blanket product endorsement.

The capability is designed around Malaysian requirements, Malaysian infrastructure and institutional collaboration.

CyberDSA is a visible milestone, but the intended outcome is durable sovereign capability development and deployment.

Required Close: Clarity on strategic fit, recommended NACSA engagement pathway and any conditions, evidence or follow-up required.

Follow-through: Document the guidance precisely and adapt subsequent positioning without overstating NACSA support.

# 6. Engagement Narrative Framework

Every stakeholder conversation should use the same strategic spine but emphasise a different institutional benefit. This prevents the initiative from becoming six separate narratives.

## 6.1 Core Narrative Spine

Core Positioning Aras Integrasi and its ecosystem partners are demonstrating the capability to design, integrate and operationalise sovereign cybersecurity technology end-to-end — delivering national-grade, full-stack protection for Malaysia’s critical digital infrastructure.

National Story: Malaysia is building the capability to develop and operationalise critical cybersecurity technology around Malaysian requirements.

Partnership Story: CSM × Aras demonstrates how institutional partnership can accelerate sovereign technology development and market activation.

Capability Story: The differentiator is integration across governance, intelligence, AI-enabled security operations and emerging-technology security.

Commercial Story: The partnership should create deployable solutions, qualified opportunities and a repeatable route to market.

Proof Story: Individual products are evidence of the capability stack, not the entire story.

## 6.2 Stakeholder-Specific Framing

| Stakeholder | Core Framing |
| --- | --- |
| Azrul Nazim | “This is a partnership outcome we can jointly demonstrate.” |
| Zulfeka bin Zainal Abidin | “This needs to convert into qualified market activity and revenue opportunity.” |
| Ts. Mohammad Zaharudin Bin Ahmad Darus | “This must be operationally executable, with clear access, owners and coordination paths.” |
| Wan Roshaimi Wan Abdullah | “This must be technically defensible, governable and integration-ready.” |
| Balamurugan Nallapan | “This validated national capability story can now be made visible and credible.” |
| Dr. Megat | “This is a maturing sovereign capability seeking the right national strategic alignment.” |

# 7. Engagement Meeting Design

The objective of each meeting is to create a decision, not merely awareness. A compact 30–45 minute format is sufficient when pre-reads and asks are clear.

| Time | Phase | Purpose |
| --- | --- | --- |
| 0–5 min | Context | Why CyberDSA matters and why this stakeholder is important to the outcome. |
| 5–12 min | Strategic Narrative | Present the integrated sovereign capability story in the stakeholder’s own institutional lens. |
| 12–25 min | Stakeholder-Specific Discussion | Address the stakeholder’s domain: partnership, commercial, operational coordination, technology/governance, market/media activation or national alignment. |
| 25–35 min | Primary Ask | Put the requested commitment clearly on the table. |
| 35–45 min | Close & Ownership | Confirm decision, next action, owner, due date and follow-up mechanism. |

## 7.1 Pre-Read Standard

Maximum two pages for senior stakeholders.

Page 1: outcome, narrative and why the stakeholder matters.

Page 2: specific ask, decisions required, immediate next steps.

Do not send product-heavy technical material unless specifically required by the stakeholder.

## 7.2 Meeting Close Discipline

Restate the agreed decision in one sentence.

Name the owner for the next action.

Set a concrete follow-up point.

Capture any concern or condition as an action item, not an unresolved discussion point.

Send written confirmation while the conversation is still fresh.

# 8. Activation Plan to CyberDSA

The following sequence is governed by stakeholder dependency rather than calendar convenience. Preparation may overlap, but each stakeholder gate should close in order before the next outward-facing commitment is treated as activated.

| Wave | Window | Lead | Action | Exit Criterion |
| --- | --- | --- | --- | --- |
| Wave 1 | Immediate | Azrul Nazim | Lock narrative direction, stakeholder sponsorship and acceptance of the governing activation sequence. | Narrative and activation sequence accepted. |
| Wave 2 | After Gate 1 | Zulfeka bin Zainal Abidin | Define target accounts, commercial success, lead flow and post-event ownership. | Commercial activation sheet agreed. |
| Wave 3 | After Gate 2 | Ts. Mohammad Zaharudin Bin Ahmad Darus | Lock operating contacts, access, implementation touchpoints, dependencies and issue-resolution path. | Operational readiness inputs defined for technical validation. |
| Wave 4 | After Gate 3 | Wan Roshaimi Wan Abdullah | Validate technical story, architecture boundaries, integration considerations, governance constraints and defensible claims. | Technical position cleared for external use. |
| Wave 5 | After Gate 4 | Balamurugan Nallapan | Build and activate the message house, media/branding plan, spokesperson alignment and approval route from the validated proposition. | Joint communications plan operational. |
| Wave 6 | After Gate 5; target Sep | Dr. Megat | Present the mature proposition and seek the appropriate NACSA strategic-alignment pathway. | NACSA guidance / pathway understood. |
| Final Integration | Final 2–3 weeks | All relevant owners | Run readiness checks across partnership, commercial, operations, technical validation, media activation and national positioning. | No unresolved P0 stakeholder dependency entering CyberDSA. |

# 9. Governance and Operating Rhythm

## 9.1 Internal Aras Control

Single accountable executive owner: Director – Cyber Security Practice.

Maintain one master stakeholder tracker; avoid separate personal trackers that fragment status.

All outbound messages must align with the agreed strategic narrative.

Escalate only material blockers: decision delay, conflicting stakeholder position, unowned dependency, or reputational risk.

## 9.2 Recommended Cadence

| Cadence | Forum | Purpose |
| --- | --- | --- |
| Weekly | Stakeholder Activation Review | Progress against the six stakeholder gates; resolve blockers; confirm the next permitted engagement in the dependency chain. |
| Weekly | Commercial Readiness | Target accounts, meetings, lead capture, POC pipeline and post-event ownership. |
| Weekly / as needed | Operational & Technical Readiness | Operational dependencies, access, architecture, governance constraints and technical clearance required before external activation. |
| Weekly → twice weekly in final 2 weeks | Marketing / Media Readiness | Messaging, approvals, media opportunities, speaker readiness and assets after technical clearance. |
| 48 hours before major engagement | Executive Brief Check | Confirm purpose, primary ask, proof points, sensitivities, prior-gate status and desired close. |

# 10. Success Metrics and Executive Dashboard

Success is measured by commitments and readiness, not by the number of meetings held.

| Workstream | Executive Stakeholder | Definition of Ready | Status |
| --- | --- | --- | --- |
| Partnership Alignment | Azrul Nazim | Narrative and activation sequence supported | Green / Amber / Red |
| Commercial Ownership | Zulfeka bin Zainal Abidin | Priority market targets and follow-up ownership agreed | Green / Amber / Red |
| Operational Enablement | Ts. Mohammad Zaharudin Bin Ahmad Darus | Contacts, access, implementation dependencies and escalation path agreed | Green / Amber / Red |
| Technical Confidence | Wan Roshaimi Wan Abdullah | Technical narrative, architecture boundaries and key constraints validated | Green / Amber / Red |
| Marketing & Media | Balamurugan Nallapan | Validated message house, activation plan and approvals operational | Green / Amber / Red |
| National Strategic Alignment | Dr. Megat | NACSA strategic pathway / guidance clarified | Green / Amber / Red |
| Overall CyberDSA Readiness | DAF / Aras | No unresolved P0 stakeholder dependency or sequence bypass | Green / Amber / Red |

## 10.1 Minimum Activation Targets Before CyberDSA

6/6 stakeholders engaged or formally routed through an agreed representative/pathway.

5/5 CSM stakeholder workstreams at Green or controlled Amber before NACSA engagement.

One approved strategic narrative carried consistently from partnership and commercial alignment through operational, technical and media outputs.

Named post-event commercial ownership for priority opportunities.

Zero ambiguity that Aras leads POC delivery support while CSM enables access, credibility and institutional coordination.

NACSA references or support, if any, represented exactly and never overstated.

# 11. Key Risks and Mitigations

| Risk | Failure Mode | Mitigation |
| --- | --- | --- |
| Fragmented CSM buy-in | Different stakeholders interpret CyberDSA as unrelated product activity. | Use Azrul Nazim’s partnership alignment as the umbrella; repeat one narrative spine in every engagement. |
| Commercial activity starts too late | Event produces visibility but weak conversion. | Secure Zulfeka bin Zainal Abidin ’s commercial model and named account owners before final event preparations. |
| Media overclaims partnership or endorsement | Public statements create governance or reputational sensitivity. | Balamurugan Nallapan activates after Wan Roshaimi Wan Abdullah’s technical close; use a controlled approval path and distinguish partnership, alignment, participation and endorsement precisely. |
| Technical team is treated as delivery resource | CSM becomes burdened with POC execution expectations. | Ts. Mohammad Zaharudin Bin Ahmad Darus defines operating boundaries and interfaces first; Wan Roshaimi Wan Abdullah validates strategy/governance; Aras remains the POC delivery owner. |
| Premature NACSA approach | Proposal appears uncoordinated or endorsement-seeking. | Engage Dr. Megat only after Azrul Nazim, Zulfeka bin Zainal Abidin , Ts. Mohammad Zaharudin Bin Ahmad Darus, Wan Roshaimi Wan Abdullah and Balamurugan Nallapan gates are materially complete. |
| Stakeholder support remains verbal | No operational follow-through. | Every meeting closes with an owner, due date and written recap. |
| Activation sequence is bypassed | Stakeholders are engaged out of order, creating contradictory asks, premature public claims or weak internal sponsorship. | Use one master tracker and enforce the governing chain: Azrul Nazim → Zulfeka bin Zainal Abidin → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan → Dr. Megat. Parallel preparation is allowed; gate closure is sequential. |

# 12. Immediate Action Register

The following actions should be treated as the activation baseline. The order is intentional.

| ID | Stakeholder | Action | Owner | Timing | Status |
| --- | --- | --- | --- | --- | --- |
| P0-01 | Azrul Nazim | Request partnership alignment session focused on CyberDSA narrative and stakeholder activation. | DAF | Now | Open |
| P0-02 | Azrul Nazim | Close on joint narrative, sponsorship and governing sequence for Zulfeka bin Zainal Abidin → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan → Dr. Megat. | DAF | Within 48h | Open |
| P0-03 | Zulfeka bin Zainal Abidin | Run commercial activation session; define target engagement, conversion logic and post-event ownership. | DAF / Sales Lead | After Azrul Nazim | Open |
| P0-04 | Ts. Mohammad Zaharudin Bin Ahmad Darus | Confirm operational coordination, access, implementation dependencies and escalation pathway required to support the agreed commercial use cases. | DAF / Delivery Lead | After Zulfeka bin Zainal Abidin | Open |
| P0-05 | Wan Roshaimi Wan Abdullah | Validate technical narrative, architecture posture, integration boundaries, governance constraints and public technical claims. | DAF / Technical Lead | After Ts. Mohammad Zaharudin Bin Ahmad Darus | Open |
| P0-06 | Balamurugan Nallapan | Run marketing/media alignment; lock message house, spokesperson roles, media plan and approval path using the technically cleared position. | DAF / Branding | After Wan | Open |
| P0-07 | Dr. Megat | Prepare NACSA strategic-alignment brief based on the mature CSM position and completed internal activation sequence. | DAF | After Gate 5 | Pending |
| P0-08 | All | Maintain weekly executive status using Green/Amber/Red readiness and explicit next-gate control. | DAF | Weekly | Open |

# 13. Executive Engagement Brief Template

Use this structure for every stakeholder engagement. It keeps preparation focused and makes the close explicit.

| Stakeholder | Name / role / influence lens |
| --- | --- |
| Purpose | Why this engagement is necessary now |
| Desired Outcome | One sentence only |
| Primary Ask | The specific commitment or decision required |
| Stakeholder Value | Why participation is useful to them / CSM / NACSA |
| Three Proof Points | Evidence supporting the narrative |
| Likely Concern | Most probable objection or sensitivity |
| Response | How the concern will be addressed without overcommitting |
| Required Close | What must be agreed before leaving the room |
| Follow-Up | Owner + date + next action |

# 14. Final Operating Principle

CyberDSA Is the Catalyst — Not the End State The desired outcome is not simply a successful event. It is a durable CSM–Aras operating relationship that can take sovereign cybersecurity capabilities from partnership sponsorship, through commercial definition, operational enablement and technical validation, into controlled market activation and national strategic alignment. Every stakeholder engagement should therefore create reusable institutional alignment that remains valuable after CyberDSA 2026.

Immediate next move: Activate Azrul Nazim first. Secure partnership and alliance sponsorship for the narrative and governing sequence, then progress deliberately through Zulfeka bin Zainal Abidin  → Ts. Mohammad Zaharudin Bin Ahmad Darus → Wan Roshaimi Wan Abdullah → Balamurugan Nallapan. Approach Dr. Megat only after those CSM gates are materially aligned and the proposition is ready for national strategic discussion.