CYBERDSA 2026

# Executive Stakeholder Engagement
& Activation Framework

Document 1 — Operational Playbook for CyberSecurity Malaysia and NACSA Stakeholder Activation

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Strategic Intent
Secure the stakeholder alignment required to position the Aras Integrasi × CyberSecurity Malaysia collaboration at CyberDSA 2026 as a credible, commercially actionable and nationally aligned sovereign cybersecurity capability.

Prepared for: Director – Cyber Security Practice, Aras Integrasi Sdn Bhd

Status: Internal Activation Framework | Version 1.0 | 19 August 2026

# 1. Executive Summary

CyberDSA 2026 is being used as an activation point for a broader strategic outcome: establishing Aras Integrasi and CyberSecurity Malaysia (CSM) as an aligned ecosystem capable of presenting, commercialising and operationalising national-grade sovereign cybersecurity technology.

The immediate priority is not additional product development. The priority is stakeholder alignment. The programme must secure the right internal CSM sponsorship, commercial ownership, market amplification, technical confidence and operational coordination before seeking higher-level national strategic alignment with NACSA.

Primary Mission Create a sequence of willing, informed and accountable stakeholders who each own a defined part of the CyberDSA outcome — partnership, commercial activation, media amplification, technical confidence, operational coordination and national strategic alignment.

## 1.1 Required End State

CSM and Aras Integrasi share one coherent CyberDSA positioning and understand the intended national-grade sovereign technology story.

Each critical stakeholder has one explicit role, one primary ask and one measurable outcome.

Commercial follow-through is designed before the event rather than improvised after the event.

Marketing and media amplification are coordinated around the same narrative and proof points.

The CSM technical leadership is confident in architecture, deployment posture and governance without being burdened with Aras-delivered POC execution.

NACSA engagement occurs only after the CSM alignment is sufficiently mature to present a credible, already-organised initiative.

## 1.2 Immediate Priority

| ACTION | Secure Azrul’s partnership and alliance buy-in for the CyberDSA narrative and use that alignment as the entry point for the remaining stakeholder sequence. |
| --- | --- |
| OWNER | DAF / Aras Integrasi |
| TIMING | Priority 1 — initiate first |

# 2. Mission, Scope and Activation Logic

Mission Objective. Engineer the stakeholder conditions required for CyberDSA 2026 to become a credible launch and market-activation platform for an integrated Malaysian sovereign cybersecurity capability, with Aras Integrasi acting as the operational technology integrator and CSM acting as a strategic ecosystem partner.

## 2.1 What This Framework Covers

Stakeholder roles and influence objectives.

Engagement sequence and dependencies.

The specific decision or commitment required from each stakeholder.

Meeting design, messaging and follow-up mechanics.

Activation governance, cadence and escalation.

Success measures and executive tracking.

## 2.2 What This Framework Does Not Cover

Detailed product architecture, development backlog or engineering delivery plan.

A standalone CyberDSA media plan or creative campaign plan.

A full post-event sales operating model.

A request for CSM technical personnel to execute Aras POCs; Aras will support and deliver the POC activity on CSM’s behalf where required.

## 2.3 Activation Doctrine

1. Align before asking — Stakeholders should first understand the intended outcome and why their role matters before receiving a task or commitment request.

2. One stakeholder, one primary ask — Avoid broad or ambiguous requests. Each engagement should close on one principal commitment.

3. Build internal coherence before external validation — CSM alignment precedes NACSA strategic alignment.

4. Make participation valuable — Each stakeholder should see a direct institutional benefit — partnership relevance, commercial opportunity, visibility, technical credibility or national contribution.

5. Convert verbal support into operating behaviour — Every positive discussion must produce a named next action, owner and follow-up date.

6. Keep the narrative integrated — The three product pillars are proof of an integrated sovereign capability, not disconnected product launches.

# 3. Stakeholder Architecture

The stakeholder model is deliberately compact. The objective is to create a clear chain of alignment rather than a large stakeholder committee with diluted accountability.

| # | Stakeholder | Role Lens | Primary Objective | Required Outcome |
| --- | --- | --- | --- | --- |
| 1 | Azrul | Partnership & Alliance | Anchor the CSM–Aras strategic partnership and secure internal sponsorship for the joint CyberDSA narrative. | Partnership buy-in and sponsorship |
| 2 | Zulfikar | Commercial | Translate the partnership narrative into market activation, priority accounts and post-event commercial follow-through. | Commercial ownership |
| 3 | Bala | Marketing & Media Engagement | Shape, coordinate and amplify the external story across branding, media and stakeholder communications. | Market visibility and message consistency |
| 4 | Wan Roshaimi | CTO / Technology Strategy | Provide technical confidence, architecture alignment and governance-level validation of the integrated capability. | Technical confidence and strategic fit |
| 5 | Zaharudin | Operational / Technical Coordination | Enable coordination, access and implementation touchpoints between CSM and Aras without shifting POC delivery responsibility to CSM. | Operational enablement |
| 6 | Dr. Megat | NACSA – National Strategic Alignment | Assess alignment of the mature proposition with national sovereign cybersecurity priorities and provide an appropriate pathway for strategic recognition/engagement. | National strategic alignment |

## 3.1 The Dependency Chain

Azrul → Zulfikar → Bala → Wan Roshaimi → Zaharudin → Dr. Megat

This sequence is not merely administrative. It progressively builds the proposition from internal partnership legitimacy to commercial relevance, market readiness, technical confidence, operational feasibility and finally national strategic alignment.

# 4. Engagement Sequence and Decision Gates

| Decision Gate | Lead Stakeholder | Close Required | Control Point |
| --- | --- | --- | --- |
| Gate 1 — Partnership Alignment | Azrul | Confirm the partnership intent, joint CyberDSA narrative and CSM sponsorship pathway. | Do not activate broader CSM asks until the partnership narrative is sufficiently stable. |
| Gate 2 — Commercial Ownership | Zulfikar | Agree what commercial success looks like, target engagement priorities and post-event follow-through. | No event activation should proceed without a conversion path. |
| Gate 3 — Market & Media Activation | Bala | Agree external messaging, spokesperson coordination, media opportunities and amplification responsibilities. | No fragmented product-by-product messaging. |
| Gate 4 — Technical Confidence | Wan Roshaimi | Validate technical posture, architecture fit, integration boundaries and governance concerns. | Technical leadership validates; Aras remains responsible for POC execution. |
| Gate 5 — Operational Coordination | Zaharudin | Agree implementation touchpoints, access, coordination and issue-resolution mechanisms. | Keep coordination light, practical and owner-based. |
| Gate 6 — National Strategic Alignment | Dr. Megat | Present a mature proposition and explore NACSA alignment, acknowledgement, participation or appropriate strategic pathway. | Approach with evidence of prior CSM alignment, not as an unformed endorsement request. |

# 5. Stakeholder Engagement Playbooks

Each playbook below is designed to produce one defined commitment. Secondary discussion points are permitted, but the primary ask should remain clear throughout the engagement.

## 5.1 Azrul — Partnership & Alliance Anchor

| Role Lens | Partnership & Alliance |
| --- | --- |
| Engagement Purpose | Position the CyberDSA initiative as a strategic CSM–Aras alliance outcome rather than a vendor-led product promotion. |
| Primary Ask | Secure Azrul’s explicit support for the joint CyberDSA narrative and his sponsorship for the relevant CSM stakeholders to participate in the activation sequence. |
| Stakeholder Value | Strengthens CSM’s partnership visibility, demonstrates tangible post-MOU execution, and creates a coherent institutional story around sovereign technology development and market activation. |

### Message Emphasis

CyberDSA should demonstrate what the CSM–Aras partnership can operationalise, not merely what individual products can do.

The collaboration can be framed as Partnership → Sovereign Technology Development → National Market Activation.

Aras will carry the execution burden; CSM’s value is strategic partnership, institutional credibility and ecosystem activation.

The immediate ask is alignment and sponsorship, not operational workload.

Required Close: Agreement on narrative direction, stakeholder activation sequence and permission/support to mobilise the commercial, marketing, technical and coordination tracks.

Follow-through: Send a short written alignment note within 24 hours, listing agreed narrative, named stakeholders and next engagements.

## 5.2 Zulfikar — Commercial Activation Owner

| Role Lens | Head of Commercial |
| --- | --- |
| Engagement Purpose | Convert the CyberDSA narrative into measurable market activity and establish a post-event commercial conversion pathway. |
| Primary Ask | Agree the priority market segments/accounts, the commercial engagement mechanism at CyberDSA and the post-event follow-up model jointly supported by CSM and Aras. |
| Stakeholder Value | Creates commercial proof that the partnership can generate market outcomes, not only event visibility. |

### Message Emphasis

The event must produce a managed pipeline, not a list of visitors.

Aras can lead demos, solutioning and POC execution; the commercial track should focus on access, prioritisation and conversion.

The strongest accounts are those where CSM credibility and Aras delivery capability create a differentiated entry point.

Post-event ownership must be agreed before the event.

Required Close: Named priority accounts/segments, clear CSM and Aras commercial owners, agreed lead-capture and follow-up mechanism, and target outcomes for meetings/POCs.

Follow-through: Create a one-page joint target-account and follow-up sheet; review weekly until CyberDSA.

## 5.3 Bala — Marketing & Media Engagement Owner

| Role Lens | Marketing & Media Engagement |
| --- | --- |
| Engagement Purpose | Create one consistent public narrative and amplify it through coordinated branding, media, content and stakeholder communications. |
| Primary Ask | Agree a joint marketing/media activation plan around the national-grade, full-stack sovereign technology deployment narrative. |
| Stakeholder Value | Positions CSM as an active national ecosystem partner and prevents fragmented or contradictory product messaging. |

### Message Emphasis

The media story is the emergence of an integrated Malaysian sovereign cybersecurity capability, not three disconnected products.

CSM’s role should be visible as an ecosystem and institutional partner while Aras is positioned as the integration and operationalisation engine.

Every public asset should reinforce the same hierarchy: national story → partnership story → integrated capability → product proof points.

Media activity should lead audiences toward meetings, demos and post-event engagement.

Required Close: Agreed message house, spokesperson roles, media/branding touchpoints, content approval path and activation calendar.

Follow-through: Run a compact editorial and media readiness checkpoint each week; move to higher cadence in the final two weeks.

## 5.4 Wan Roshaimi — Technology Strategy & Governance

| Role Lens | CTO / Technology Strategy |
| --- | --- |
| Engagement Purpose | Establish technical credibility and strategic architecture alignment without transferring Aras delivery obligations to the CSM technical team. |
| Primary Ask | Validate the technical narrative, integration posture, architecture principles and key governance considerations that should be represented at CyberDSA. |
| Stakeholder Value | Gives CSM confidence that the proposition is technically defensible and appropriately aligned with its technology environment and institutional responsibilities. |

### Message Emphasis

Aras will support and execute the POC activity; CSM technical leadership is not being asked to provide POC delivery resources.

The CTO engagement is about architecture, governance, integration boundaries and long-term fit.

Technical claims presented publicly must be accurate, defensible and consistent with the intended deployment model.

Any integration dependencies should be surfaced early so they can be managed before the event.

Required Close: Technical narrative validation, explicit integration considerations, identified red lines/constraints and agreement on any technical representation required at CyberDSA.

Follow-through: Capture decisions in a technical alignment note and route all execution actions back to Aras owners.

## 5.5 Zaharudin — Operational Coordination & Enablement

| Role Lens | Operational / Technical Coordination |
| --- | --- |
| Engagement Purpose | Ensure practical CSM–Aras coordination is smooth, accountable and responsive without creating unnecessary process overhead. |
| Primary Ask | Agree the operational touchpoints, access requirements, contact chain and issue-resolution path necessary to support CyberDSA readiness and related POC activity led by Aras. |
| Stakeholder Value | Reduces coordination friction and ensures CSM stakeholders can support the initiative through access and enablement rather than direct execution. |

### Message Emphasis

The aim is to make execution easy for both organisations.

Aras owns POC delivery; CSM enables relevant access, coordination and institutional interfaces.

Issues should have a named owner and fast resolution path rather than being allowed to circulate across multiple teams.

Operational coordination should support the agreed partnership narrative, not become a parallel workstream.

Required Close: Named operational contacts, agreed coordination channel, access requirements, issue escalation path and near-term readiness actions.

Follow-through: Maintain a short action register with owner, due date and status; escalate only unresolved blockers.

## 5.6 Dr. Megat — NACSA Strategic Alignment for Sovereign Product

| Role Lens | National Strategic Alignment |
| --- | --- |
| Engagement Purpose | Position the integrated proposition within the broader national cybersecurity context once CSM alignment is mature and internally coherent. |
| Primary Ask | Seek strategic alignment on the sovereign capability direction and identify the appropriate form of NACSA engagement — acknowledgement, participation, policy alignment, evaluation pathway or other suitable mechanism. |
| Stakeholder Value | Provides a pathway for the initiative to be understood in the context of national priorities without overreaching into a premature or transactional endorsement request. |

### Message Emphasis

The proposition should be presented as a Malaysian capability that has already progressed through partnership, commercial, media, technical and operational alignment.

The request is for strategic alignment and the appropriate national pathway, not a blanket product endorsement.

The capability is designed around Malaysian requirements, Malaysian infrastructure and institutional collaboration.

CyberDSA is a visible milestone, but the intended outcome is durable sovereign capability development and deployment.

Required Close: Clarity on strategic fit, recommended NACSA engagement pathway and any conditions, evidence or follow-up required.

Follow-through: Document the guidance precisely and adapt subsequent positioning without overstating NACSA support.

# 6. Engagement Narrative Framework

Every stakeholder conversation should use the same strategic spine but emphasise a different institutional benefit. This prevents the initiative from becoming six separate narratives.

## 6.1 Core Narrative Spine

Core Positioning Aras Integrasi and its ecosystem partners are demonstrating the capability to design, integrate and operationalise sovereign cybersecurity technology end-to-end — delivering national-grade, full-stack protection for Malaysia’s critical digital infrastructure.

National Story: Malaysia is building the capability to develop and operationalise critical cybersecurity technology around Malaysian requirements.

Partnership Story: CSM × Aras demonstrates how institutional partnership can accelerate sovereign technology development and market activation.

Capability Story: The differentiator is integration across governance, intelligence, AI-enabled security operations and emerging-technology security.

Commercial Story: The partnership should create deployable solutions, qualified opportunities and a repeatable route to market.

Proof Story: Individual products are evidence of the capability stack, not the entire story.

## 6.2 Stakeholder-Specific Framing

| Stakeholder | Core Framing |
| --- | --- |
| Azrul | “This is a partnership outcome we can jointly demonstrate.” |
| Zulfikar | “This needs to convert into qualified market activity and revenue opportunity.” |
| Bala | “This is a national capability story that can be made visible and credible.” |
| Wan Roshaimi | “This must be technically defensible, governable and integration-ready.” |
| Zaharudin | “This must be easy to coordinate and execute without unnecessary friction.” |
| Dr. Megat | “This is a maturing sovereign capability seeking the right national strategic alignment.” |

# 7. Engagement Meeting Design

The objective of each meeting is to create a decision, not merely awareness. A compact 30–45 minute format is sufficient when pre-reads and asks are clear.

| Time | Phase | Purpose |
| --- | --- | --- |
| 0–5 min | Context | Why CyberDSA matters and why this stakeholder is important to the outcome. |
| 5–12 min | Strategic Narrative | Present the integrated sovereign capability story in the stakeholder’s own institutional lens. |
| 12–25 min | Stakeholder-Specific Discussion | Address the stakeholder’s domain: partnership, commercial, media, technology, operations or national alignment. |
| 25–35 min | Primary Ask | Put the requested commitment clearly on the table. |
| 35–45 min | Close & Ownership | Confirm decision, next action, owner, due date and follow-up mechanism. |

## 7.1 Pre-Read Standard

Maximum two pages for senior stakeholders.

Page 1: outcome, narrative and why the stakeholder matters.

Page 2: specific ask, decisions required, immediate next steps.

Do not send product-heavy technical material unless specifically required by the stakeholder.

## 7.2 Meeting Close Discipline

Restate the agreed decision in one sentence.

Name the owner for the next action.

Set a concrete follow-up point.

Capture any concern or condition as an action item, not an unresolved discussion point.

Send written confirmation while the conversation is still fresh.

# 8. Activation Plan to CyberDSA

The following sequence is designed for immediate execution from 19 August 2026. Dates can be compressed as required, but the dependency order should be preserved.

| Wave | Window | Lead | Action | Exit Criterion |
| --- | --- | --- | --- | --- |
| Wave 1 — Partnership Lock | 19–24 Aug | Azrul | Lock narrative direction and stakeholder sponsorship. | Narrative and activation sequence accepted. |
| Wave 2 — Commercial Activation | 24–31 Aug | Zulfikar | Define target accounts, lead flow and post-event ownership. | Commercial activation sheet agreed. |
| Wave 3 — Market & Media Alignment | 24 Aug–7 Sep | Bala | Build message house, media/branding plan and approval route. | Joint communications plan operational. |
| Wave 4 — Technical Confidence | 31 Aug–10 Sep | Wan Roshaimi | Validate technical story, boundaries and integration considerations. | Technical position cleared. |
| Wave 5 — Operational Readiness | 1–15 Sep | Zaharudin | Lock coordination, access and issue-resolution path. | Readiness action register active. |
| Wave 6 — National Alignment | After CSM alignment; target Sep | Dr. Megat | Present mature proposition and seek strategic alignment pathway. | NACSA guidance / pathway understood. |
| Final Integration | Final 2–3 weeks | All relevant owners | Run readiness checks across narrative, commercial, media, technical and operations. | No unresolved P0 stakeholder dependency entering CyberDSA. |

# 9. Governance and Operating Rhythm

## 9.1 Internal Aras Control

Single accountable executive owner: Director – Cyber Security Practice.

Maintain one master stakeholder tracker; avoid separate personal trackers that fragment status.

All outbound messages must align with the agreed strategic narrative.

Escalate only material blockers: decision delay, conflicting stakeholder position, unowned dependency, or reputational risk.

## 9.2 Recommended Cadence

| Cadence | Forum | Purpose |
| --- | --- | --- |
| Weekly | Stakeholder Activation Review | Progress against six stakeholder outcomes; resolve blockers; set next engagements. |
| Weekly | Commercial Readiness | Target accounts, meetings, lead capture, POC pipeline and follow-up readiness. |
| Weekly → twice weekly in final 2 weeks | Marketing / Media Readiness | Messaging, approvals, media opportunities, speaker readiness and assets. |
| As needed | Technical / Operational Issue Resolution | Only for identified architecture, access or coordination blockers. |
| 48 hours before major engagement | Executive Brief Check | Confirm purpose, primary ask, proof points, sensitivities and desired close. |

# 10. Success Metrics and Executive Dashboard

Success is measured by commitments and readiness, not by the number of meetings held.

| Workstream | Executive Stakeholder | Definition of Ready | Status |
| --- | --- | --- | --- |
| Partnership Alignment | Azrul | Narrative and activation sequence supported | Green / Amber / Red |
| Commercial Ownership | Zulfikar | Priority market targets and follow-up ownership agreed | Green / Amber / Red |
| Marketing & Media | Bala | Message house, activation plan and approvals operational | Green / Amber / Red |
| Technical Confidence | Wan Roshaimi | Technical narrative and key constraints validated | Green / Amber / Red |
| Operational Coordination | Zaharudin | Contacts, access and escalation path agreed | Green / Amber / Red |
| National Strategic Alignment | Dr. Megat | NACSA strategic pathway / guidance clarified | Green / Amber / Red |
| Overall CyberDSA Readiness | DAF / Aras | No unresolved P0 stakeholder dependency | Green / Amber / Red |

## 10.1 Minimum Activation Targets Before CyberDSA

6/6 stakeholders engaged or formally routed through an agreed representative/pathway.

5/5 CSM stakeholder workstreams at Green or controlled Amber before NACSA engagement.

One approved strategic narrative used consistently across partnership, commercial and media materials.

Named post-event commercial ownership for priority opportunities.

Zero ambiguity that Aras leads POC delivery support while CSM enables access, credibility and institutional coordination.

NACSA references or support, if any, represented exactly and never overstated.

# 11. Key Risks and Mitigations

| Risk | Failure Mode | Mitigation |
| --- | --- | --- |
| Fragmented CSM buy-in | Different stakeholders interpret CyberDSA as unrelated product activity. | Use Azrul’s partnership alignment as the umbrella; repeat one narrative spine in every engagement. |
| Commercial activity starts too late | Event produces visibility but weak conversion. | Secure Zulfikar’s commercial model and named account owners before final event preparations. |
| Media overclaims partnership or endorsement | Public statements create governance or reputational sensitivity. | Bala-led approval path; distinguish partnership, alignment, participation and endorsement precisely. |
| Technical team is treated as delivery resource | CSM becomes burdened with POC execution expectations. | State explicitly that Aras owns POC delivery; Wan Roshaimi validates strategy/governance and Zaharudin enables coordination. |
| Premature NACSA approach | Proposal appears uncoordinated or endorsement-seeking. | Engage Dr. Megat after CSM alignment gates are substantially complete. |
| Stakeholder support remains verbal | No operational follow-through. | Every meeting closes with an owner, due date and written recap. |
| Too many parallel conversations | Conflicting messages and duplicated asks. | Single owner and master tracker; sequence engagements and record decisions centrally. |

# 12. Immediate Action Register

The following actions should be treated as the activation baseline. The order is intentional.

| ID | Stakeholder | Action | Owner | Timing | Status |
| --- | --- | --- | --- | --- | --- |
| P0-01 | Azrul | Request partnership alignment session focused on CyberDSA narrative and stakeholder activation. | DAF | Immediate | Open |
| P0-02 | Azrul | Close on joint narrative, sponsorship and sequence for Zulfikar, Bala, Wan Roshaimi and Zaharudin. | DAF | Within 48h of session | Open |
| P0-03 | Zulfikar | Run commercial activation session; define target engagement and post-event ownership. | DAF / Sales Lead | After Azrul alignment | Open |
| P0-04 | Bala | Run marketing/media alignment; lock message house, media plan and approval path. | DAF / Branding | After narrative lock | Open |
| P0-05 | Wan Roshaimi | Validate technical narrative, architecture posture and governance boundaries. | DAF / Technical Lead | After core narrative lock | Open |
| P0-06 | Zaharudin | Confirm operational coordination, access and escalation pathway. | DAF / Delivery Lead | In parallel with technical readiness | Open |
| P0-07 | Dr. Megat | Prepare NACSA strategic-alignment brief based on mature CSM position. | DAF | After CSM gates substantially complete | Pending dependency |
| P0-08 | All | Maintain weekly executive status using Green/Amber/Red readiness. | DAF | Weekly to CyberDSA | Open |

# 13. Executive Engagement Brief Template

Use this structure for every stakeholder engagement. It keeps preparation focused and makes the close explicit.

| Stakeholder | Name / role / influence lens |
| --- | --- |
| Purpose | Why this engagement is necessary now |
| Desired Outcome | One sentence only |
| Primary Ask | The specific commitment or decision required |
| Stakeholder Value | Why participation is useful to them / CSM / NACSA |
| Three Proof Points | Evidence supporting the narrative |
| Likely Concern | Most probable objection or sensitivity |
| Response | How the concern will be addressed without overcommitting |
| Required Close | What must be agreed before leaving the room |
| Follow-Up | Owner + date + next action |

# 14. Final Operating Principle

CyberDSA Is the Catalyst — Not the End State The desired outcome is not simply a successful event. It is a durable CSM–Aras operating relationship that can take sovereign cybersecurity capabilities from partnership formation, through technical and commercial validation, into national market activation. Every stakeholder engagement should therefore create reusable institutional alignment that remains valuable after CyberDSA 2026.

Immediate next move: Activate Azrul first. Secure partnership and alliance buy-in for the narrative, obtain sponsorship for the stakeholder sequence, and then move deliberately through commercial, media, technical and operational alignment before approaching Dr. Megat for NACSA strategic alignment.